## Sheet1
S. No | Project | Client | Items | Status | PO Value | Total Billing Ammount | Pending Amount | PO Date | Project Period | Technical Manager
1 | NTPC- Ecopark | RIC | CCTV | In Progres | 73000000 | 47072121.5 | 25927878.5 | 2022-05-27 | 3 years, 7 months, 9 days | Puran
2 | NCDC- HSCC | Dyna Filter | CCTV, FAS, BMS | In Progres | 8250965 | 2317975 | 5932990 | 2024-01-20 | 1 years, 11 months, 13 days | Satish
3 | TATA Power tamil Nadu | Voltas | BMS | In Progres | Not found | Not found | 0 | 0 | 0 | Anil
4 | Trump Tower M3M Grugaon | M3M | BGM | In Progres | 480000 | 363200 | 116800 | 2024-03-28 | 1 years, 9 months, 5 days | Mahipal
5 | AIIMS - Delhi | Krishna Const. | CCTV, FAS, PA, EPBAX | In Progres | 12281602 | 1702120 | 10579482 | 2024-05-23 | 1 years, 7 months, 10 days | Satish
6 | M3M - Panipat | M3M | Boom Barriers | In Progres | 2468800 | 1520960 | 947840 | 2024-07-19 | 1 years, 5 months, 14 days | Mahipal
7 | M3M- Capitol -113 R&R | M3M | CCTV , Boom , Access | In Progres | 11734161 | 2063038 | 9671123 | 2024-07-16 | 1 years, 5 months, 17 days | Mahipal
9 | AB Mauri | Bluestar | FAS | In Progres | 6925030 | 6100020 | 825010 | 2024-07-16 | 1 years, 5 months, 17 days | Satish
10 | ITO Mumbai | SPG | FAS PA | In Progres | 6100585 | 5874560 | 226025 | 2024-07-03 | 0 | Vijay Satish - Technical
11 | ITO Mumbai | SPG | BMS | In Progres | 6350710 | 4403434 | 1947276 | 2024-11-18 | 1 years, 1 months, 15 days | Vijay Satish - Technical
12 | Jammu Railway Station | MRC | BMS | In Progres | 3114148 | 1991665 | 1122483 | 2024-12-09 | 1 years, 0 months, 24 days | Satish
13 | Grandthum Ref.No.289 (A) | Bhutani Group | CCTV | In Progres | 31196662 | 13194688 | 18001974 | 2024-12-04 | 1 years, 0 months, 29 days | Ram, Pooran
14 | Grandthum Ref.No.309 | Bhutani Group | Swing Barrier | In Progres | 8005040 | 6949152 | 1055888 | 2025-05-12 | 0 years, 7 months, 21 days | Ram, Pooran
15 | GGSIPU | Labotek | FAS, PA, | In Progres | 907796 | 761325 | 146471 | 16-04-2025 | 0 years, 8 months, 17 days | Sanjay
16 | Max saket | Hietachi | BMS | In Progres | 10788650 | 4671318 | 6117332 | 2025-03-18 | 0 years, 9 months, 15 days | Ajay Chuahan, Vijay, Ravinder Sir
17 | M3M- Jewel (Ref.297) | M3M | CCTV , Boom , ACS | In Progres | 2832390 | 382627 | 2449763 | 2025-01-22 | 0 years, 11 months, 11 days | Mahipal
18 | M3M- Jewel | M3M | Music | In Progres | 1126004 | 114450 | 1011554 | 2025-01-20 | 0 years, 11 months, 13 days
19 | M3M- Paragon (296) | M3M | CCTV, Boom Barrier, ACS | In Progres | 4100000 | 435313 | 3664687 | 2025-02-24 | 0 years, 10 months, 19 days
20 | M3M- Paragon (295) | M3M | Music Systen | In Progres | 3699991 | 267050 | 3432941 | 2025-01-20 | 0 years, 11 months, 13 days | Mahipal
21 | Max Mohali | Hitachi | BMS | In Progres | 5247334 | 3592424 | 1654910 | 2025-03-04 | 0 years, 9 months, 29 days | Ravinder Sir
22 | Max Mohali | Ahluwalia | ACS | In Progres | 5232900 | 4179540 | 1053360 | 2025-04-11 | 0 years, 8 months, 22 days | Mahipal
23 | Central Park | Kabir | CCTV | In Progres | 2728200 | 1077501 | 435313 | 2025-03-20 | 0 years, 9 months, 13 days | Vijay
24 | Central Park Flower Valley | Crystaltown | CCTV | In Progres | 639823 | 639827 | -4 | 21-8-25 | 0 years, 4 months, 12 days | Vijay
25 | Max Gurgaon (Ref.315) | Sterling Wilson | BMS | To Be Start | 7400000 | 1816482 | 5583518 | 14-07-2025 | 0 years, 5 months, 19 days | Ravinder Sir
26 | NIPL Panipat | M3M | Boom Barriers | In Progres | 10389046 | 7625072 | 2763974 | 2025-01-07 | 0 years, 11 months, 26 days | Mahipal
27 | NIPL Panipat | M3M | CCTV | To Be Start | 10389046 | 0 | 0 | 2025-10-13 | 0 years, 2 months, 20 days
28 | Karaoke | M3M | Music | To Be Start | 360000 | 0 | 0 | 2025-08-08 | 0 years, 4 months, 25 days | Mahipal
29 | Corner Walk | M3M | CCTV | In Progres | 922583 | 621833 | 0 | 2025-03-25 | 0 years, 9 months, 8 days | Vijay
30 | RFL - 9 (326)Service | Relaxo | CCTV | In Progres | 78530 | 0 | 0 |  | 0
31 | RFL - 9 (327)Supply | Relaxo | CCTV | In Progres | 450455 | 427155 | 0 |  | 0
32 | RFL - 6 (328)(service+supply) | Relaxo | CCTV | In Progres | 248525 | 2126556 | 0 |  | 0
33 | OMAXE- Hazratganj(329) | Omaxe | CCTV | To Be Start | 737756 | 0 | 0 | 2025-03-09 | 0 years, 9 months, 24 days
34 | OMAXE Bahadur Garh (332) | Omaxe | CCTV | To Be Start | 1694224 | 0 | 0 | 2025-09-22 | 0 years, 3 months, 11 days
35 | OMAXE Chandigarh-Isabela (333) | Omaxe | CCTV | To Be Start | 289083 | 0 | 0 | 2025-09-22 | 0 years, 3 months, 11 days
36 | OMAXE Chandigarh-Emred-C (334) | Omaxe | CCTV | To Be Start | 289083 | 0 | 0 | 2025-09-22 | 0 years, 3 months, 11 days
37 | DRDO - Srinigar ( Oscar) | Vishal Infra | CCTV | To Be Start | 2829825 | 0 | 0 | 2025-10-17 | 0 years, 2 months, 16 days
39 | MSME Technology Center Durg | Rounak India | ELV Work (ACS,CCTV,PA) | To Be Start | 0 | 0 | 0 | 2025-08-20
[5 empty] | 243288947 | 122291406.5 | 104668588.5

## Till Dec Billing
Summary of Old & New PO Balance, FY25-26 Billing Details
Billing Details (FY_2025-26) Reporting date:31-12-2025
Total> | [6 empty] | 109343401.2 | 76986760 | 186330161.2 |  | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Credit Note | Credit Note | Credit Note | Credit Note | Credit Note | Credit Note | Total Billing till 31-12-2025 | Billing_% | 123096285.45 | Report till 31-12-2025.
Sr.No. | Cleint's Name | Project-24-25 & 25-26 | PO Number | PO Date will be fill | PO Value | Bill till FY-24-25 | OLD PO Balance | PO Value (25-26) | Total PO Value in hand | 01st Material Delivery Date | Apr'2025 | May'2025 | Jun'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Dec'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Dec'2025 | as of now after less Credit Note | %tage of PO Value's Billing | PO_Balance in hand | Billing Type | Project Head Name | Remarks
1 | Angel Hyaat | 24-25 |  |  | 1859780 | 1574780 | 285000 | 0 | 285000 |  | 0 | [14 empty] | 0 | 0 | 285000 |  | Satish Ji | full and final Bill for FAS & PA
2 | Krihsna Aiims | 24-25 |  |  | 12281602 | 1260654 | 11020948 | 0 | 11020948 |  | 0 |  |  | 441466.9 | [11 empty] | 441466.9 | 4.0057 | 10579481.1 |  | Satish Ji
3 | Trump Tower | 24-25 |  |  | 480000 | 363200 | 116800 | 0 | 116800 |  | 0 | [14 empty] | 0 | 0 | 116800 |  | Mahipal
4 | SCO-113 Lekh | 24-25 & 25-26 |  |  | 1675761 | 1023779.3 | 651981.7 | 473318 | 1125299.7 |  | 0 |  |  |  |  | 340990 |  | 416432 | [5 empty] | 282440 |  | 474982 | 42.2094 | 650317.7 |  | Mahipal | RA-05th(CCTV Full and Final Biil is done Invoice to be raise
5 | M3M R& R | 24-25 |  |  | 11734161 | 1037342.5 | 10696818.5 | 0 | 10696818.5 |  | 0 |  |  | 1025696 | [11 empty] | 1025696 | 9.5888 | 9671122.5 |  | Mahipal
6 | M3M-Panipat-Old | 24-25 |  |  | 2468800 | 735280 | 1733520 | 0 | 1733520 |  | 0 | [6 empty] | 785680 | 67050 | [6 empty] | 852730 | 49.1907 | 880790 |  | Mahipal | Ra done, Invoice to be raise. | 114214502.1
7 | Blue Star-AB Mauri | 24-25 |  |  | 6925030 | 3262387 | 3662643 | 2438531 | 6101174 |  | - | - | 974211 | 203431.85 |  |  |  | 1668274 | 199014 | 8283 | [5 empty] | 3036647.85 | 49.7715 | 3064526.15 |  | Satish | RA-06th (MB bill to be raise Invoice.
8 | M3M JEWEL - Music System | 24-25 |  |  | 1126004 | 0 | 1126004 | 0 | 1126004 |  | 0 |  |  |  |  | 114450 | [9 empty] | 114450 | 10.1643 | 1011554 |  | Mahipal
9 | M3M -Paragon - Music System | 24-25 |  |  | 3699991 | 0 | 3699991 | 0 | 3699991 |  | 0 |  |  |  |  | 267050 | [9 empty] | 267050 | 7.2176 | 3432941 |  | Mahipal
10 | M3M -Jewel Security System | 24-25 | Lekh/Jewel 25/Security System and Access Control Work/LOA/2025/26 |  | 2832390 | 0 | 2832390 | 0 | 2832390 |  | 0 |  |  |  | 158790 | 110642 |  | 271985 |  |  |  | 158790 |  |  |  | 382627 | 13.509 | 2449763 | Supply | Mahipal | RA-01st Invoice to be raise
11 | M3M -Paragon-57 Security System | 24-25 | Paryapt/Paragon-57/Security System and Access Control Work/LOA/2025/81 |  | 4100000 | 0 | 4100000 | 0 | 4100000 |  | 0 |  |  |  | 223703 | 152303 |  | 283010 |  |  |  | 223703 |  |  |  | 435313 | 10.6174 | 3664687 | Supply | Mahipal | RA-01st Invoice to be raise
12 | M3M -Corner Walk-Prompt-CCTV |  | Prompt/Corner Walk/SITC/of CCTV Work for Loft Area/LOA/2024/343 |  | 922583 | 0 | 0 | 1139219 | 1139219 |  | 0 | 0 |  |  | 413295 | 208538 |  |  | 123170 | [6 empty] | 745003 | 65.3959 | 394216 |  | Mr Pooran
13 | Labotek GGIPU | 24-25 |  |  | 907796 | 0 | 907796 | 0 | 907796 |  | 0 | 427607 |  | 333718 | [11 empty] | 761325 | 83.8652 | 146471 |  | Mr Prakash
14 | Power House Jhajjar | 24-25 |  |  | 780500 | 205595 | 574905 | 0 | 574905 |  | 130500 | [14 empty] | 130500 | 22.6994 | 444405 |  | Ashu | Completed "The payment is still pending
13 | SPG-ITO Mumbai-ELV | 24-25 |  |  | 6100585 | 3683520 | 2417065 | 0 | 2417065 |  |  |  | 1443970 | 576963 |  |  |  | 170107 | [7 empty] | 2191040 | 90.6488 | 226025 |  | Satish Ji & Vijay | Invoice to be raise
14 | SPG-ITO Mumbai-BMS | 24-25 |  |  | 6350710 | 3293305 | 3057405 | 0 | 3057405 |  | 0 | 510195 | 203362 | 266912 |  | 79040 |  | 50620 | [7 empty] | 1110129 | 36.3095 | 1947276 | Supply | Satish Ji & Pooran | Invoice to be raise
15 | MRC-Jammu | 24-25 |  |  | 3114148 | 1296490 | 1817658 | 0 | 1817658 |  | 695175 | [14 empty] | 695175 | 38.2456 | 1122483 | Supply | Satish Ji | Invoice raised.
18 | RFL-AMC-Q4 | 24-25 |  |  | 2750000 | 2062500 | 687500 | 0 | 687500 |  |  | 687500 | [13 empty] | 687500 | 100 | 0 |  | Sayed & Sandeep | PO Completed
16 | AL SOFTWEB - Grandthum_CCTV Bhutani Group | 24-25 |  |  | 31196662 | 7470651 | 23726011 | 0 | 23726011 |  | 0 | 1254829 | 2017195 |  | 0 | 1709426 | 742587 |  |  |  |  | 0 |  |  | 11705 | 5712332 | 24.0762 | 18013679 |  | Pooran Ji | RA-09th done, Invoice to be raise Check and approval pending from Cleint side.
17 | RIC-Eco Park | to old |  |  | 73000000 | 44279628 | 28720372 | 0 | 28720372 | [5 empty] | 411862.5 | 1984800 |  | 395831 | 246862 | [6 empty] | 3039355.5 | 10.5826 | 25681016.5 |  | Pooran Ji | MB RA03rd Bill is Pending due to Client side.
20 | SPG-Hanumnagarh | to old |  |  | 20680085 | 16246740 | 4433345 | 0 | 4433345 |  |  |  |  | 4433345 | [11 empty] | 4433345 | 100 | 0 |  | Pooran Ji | Completed
21 | NCDC-Dyna Filters-ELV | to old |  |  | 3018195 | 2317975 | 700220 | 0 | 700220 | [16 empty] | 0 | 0 | 700220 |  | Satish Ji
22 | NCDC-Dyna Filters-BMS | to old |  |  | 5232770 | 2902732 | 2330038 | 0 | 2330038 | [16 empty] | 0 | 0 | 2330038 |  | Satish Ji
18 | Max Saket-Delhi- BMS-Hitachi | 25-26 |  | 2025-04-01 | 10788650 | 0 | 0 | 10788650 | 10788650 | 2025-04-15 | 0 | 3385398 | 583224 | 11281 | 550862 | 185914 |  | 723777 |  | 583224 |  |  |  | 185914 |  | 4671318 | 43.2984 | 6117332 | Supply | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
19 | Max-Mohali- Acces Control Ahluwalia | 25-26 |  | 2025-04-01 | 5232900 | 0 | 0 | 5232900 | 5232900 | 2025-05-28 | - | 1376859 | 300933 |  | 219678 | 1934090 |  | 347980 | [7 empty] | 4179540 | 79.8704 | 1053360 |  | Mr Pooran | RA5th_ Done Invocie to be raise
20 | Max-Mohali-BMS-Hitachi | 25-26 |  | 2025-04-01 | 5247334 | 0 | 0 | 5247334 | 5247334 | 2025-05-11 | - | 2191333 | 490918 |  | 625792 | 567165 |  | 208134 |  | 490918 | [5 empty] | 3592424 | 68.4619 | 1654910 |  | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
21 | Central Park-Old | 25-26 |  | 2025-04-01 | 2728200 | 0 | 0 | 2728200 | 2728200 | 2025-07-21 | [5 empty] | 236577 |  | 840924 | 134964 | [6 empty] | 1212465 | 44.4419 | 1515735 |  | Pooran Ji | RA-03rd done Invocie to be Raise
27 | Nestle AMC for 2 Site Patna & Serampore | Tally |  | 2025-04-01 | 230765 | 0 | 0 | 230765 | 230765 |  | 55100 | -55000 | [6 empty] | 55000 | [6 empty] | 55100 | 23.8771 | 175665 |  | Sandeep Kaur | SES Pending Cancelled this PO
22 | Hari Electric Work | Tally | 0 |  | 10920 | 0 | 0 | 10920 | 10920 |  | 10920 | 0 | 0 | [12 empty] | 10920 | 100 | 0 |  |  | Completed
28 | Nestle Bhiwandi | Tally |  |  | 17990 | 0 | 17990 | 0 | 17990 |  | 17990 | [14 empty] | 17990 | 100 | 0 |  | Sandeep Kaur | Completed
29 | Nestle Ponda-Goa | Tally |  |  | 17990 | -9010 | 27000 | 0 | 27000 |  | 27000 | 0 | [13 empty] | 27000 | 100 | 0 |  | Ashu | Completed
30 | Labotek GGIPU | Tally |  | 2025-04-01 | 184741 | 0 | 0 | 184741 | 184741 |  | 156460 | 0 | [13 empty] | 156460 | 84.6915 | 28281 |  | Mr Prakash
31 | Leighton Contactors | 25-26 |  | 2025-05-21 | 1873300 | 0 | 0 | 1873300 | 1873300 | 2025-05-03 | 360250 | 936650 | 576400 | [12 empty] | 1873300 | 100 | 0 |  | HSS | Completed
32 | Angel-Ramai-Haryana | Tally | Against V9's Quote | 2025-04-22 | 263090 | 0 | 0 | 263090 | 263090 |  | 0 | 263090 | [13 empty] | 263090 | 100 | 0 |  | Sanjay | Completed
33 | Embrace Infrasys | Tally | EIPL-PO-252606 | 2025-05-15 | 125000 | 125000 | 0 | 125000 | 125000 |  |  | 0 | 125000 | [12 empty] | 125000 | 100 | 0 |  |  | Completed
22 | Grandthum-Access Control | 25-26 | ALSPL/V9/SB/25- 26/WO/-8 | 2025-05-12 | 8005040 | 0 | 0 | 8005040 | 8005040 | 2025-06-11 |  |  |  | 3079200 |  | 3869952 | [9 empty] | 6949152 | 86.8097 | 1055888 |  |  | RA-03rd done Invocie to be Raise on Jan'25
35 | DPS School | 25-26 |  | 2025-05-26 | 1050457 | 0 | 0 | 1050457 | 1050457 | 2025-06-04 |  |  |  |  | 1078161 | [5 empty] | 329278 |  |  |  |  | 748883 | 71.2912 | 301574 |  |  | PI Prepare Bill to be raise on Jul'25 MB Verifcation is pending from Pooran
36 | Marada-Nestle Serampore-Service Call | Tally | - |  | 10000 | 0 | 0 | 10000 | 10000 |  |  |  | 10000 | [12 empty] | 10000 | 100 | 0 |  |  | Completed
37 | GVD-Switch Billing | Tally | - |  | 197750 | 0 | 0 | 197750 | 197750 |  |  |  | 5250 | 192500 | [11 empty] | 197750 | 100 | 0 |  |  | Completed
23 | STERLING-Max Gurgaon | 25-26 | 4900000812 | 2025-07-14 | 7400000 | 0 |  | 7400000 | 7400000 | 2025-11-26 | [7 empty] | 1816482 | 2612420 | [6 empty] | 4428902 | 59.85 | 2971098
25 | Nestle Raipur- Paid Service | Tally | 4561970433 |  | 10000 | 0 |  | 10000 | 10000 | [16 empty] | 0 | 0 | 10000
26 | Nestle Kheda-Paid | Tally | 4561931385 |  | 20000 | 0 |  | 20000 | 20000 | [16 empty] | 0 | 0 | 20000
24 | Nestle (Ganaur) | 25-26 | 4561964158 | 2025-07-17 | 1430300 | 0 |  | 1430300 | 1430300 | 2025-07-29 | [6 empty] | 1430300 | [8 empty] | 1430300 | 100 | 0 |  |  | Completed
28 | Avl India Pvt ltd | 25-26 | 40375984 | 2025-07-18 | 148000 | 0 |  | 148000 | 148000 | 2025-08-05 |  |  |  |  | 74000 |  |  |  | 74000 | [5 empty] | 74000 | 74000 | 50 | 74000
29 | Olive karoke | 25-26 | Music System | 2025-08-18 |  | 0 |  | 360000 | 360000 | 2025-12-23 | [15 empty] | 0 | 0 | 360000 |  |  | RA-01st Done, Invocie to be Raise.
25 | Nilp Panipat-Boom Barrier | 25-26 | UTTIRNA/PANIPAT PH-2/SITC Of Automatic BoomBarrier/LOA/2025/68 | 2025-07-01 | 10389046 | 0 |  | 10389046 | 10389046 | 2025-08-20 |  |  |  |  | 5649316 | 283605 |  | 1692151 | 473280 | [6 empty] | 8098352 | 77.9509 | 2290694 |  |  | Ra done Materil to be deliver
45 | Pixel Info | Tally | Return |  |  | 0 |  | 46300 | 46300 |  |  |  |  | 46300 | [11 empty] | 46300 | 100 | 0 |  |  | Done
26 | Crystaltown_New | 25-26 | 2000003682, Date:21-08-2025 | 2025-08-21 | 639823 | 0 |  | 639823 | 639823 | 2025-09-17 | [6 empty] | 153540 | 894810.35 | [5 empty] | 408523.35 |  | 639827 | 100.0006 | -4 |  |  | Completed
47 | RELAXO RFL-6 | 25-26 | 2300018047 | 2025-09-01 | 31480 | 0 |  | 31480 | 31480 | 2025-12-31 | [8 empty] | 31480 | [6 empty] | 31480 | 100 | 0 |  |  | Completed
48 | RELAXO RFL- 9 | 25-26 | 2300018052 | 2025-09-01 | 18550 | 0 |  | 18550 | 18550 | 2025-10-03 | [15 empty] | 0 | 0 | 18550 |  |  | Completed
49 | RELAXO RFL- 9 | 25-26 | 2300018053 | 2025-09-01 | 59980 | 0 |  | 59980 | 59980 | 2025-12-31 | [8 empty] | 59980 | [6 empty] | 59980 | 100 | 0 |  |  | Completed
27 | RELAXO RFL - 9 | 25-26 | 1300005422 | 2025-09-01 | 331415 | 0 |  | 331415 | 331415 | 2025-10-03 | [6 empty] | 308865 | [8 empty] | 308865 | 93.1958 | 22550 |  |  | Completed
28 | RELAXO -MD House RK Dua | Tally |  |  | 16490 | 0 |  | 16490 | 16490 | [7 empty] | 16490 | [8 empty] | 16490 | 100 | 0 |  |  | Completed
29 | RELAXO RFL - 9 | 25-26 | 1300005423 | 2025-09-01 | 119040 | 0 |  | 119040 | 119040 | 2025-10-08 | [6 empty] | 118290 | [8 empty] | 118290 | 99.37 | 750 |  |  | Completed
30 | RELAXO RFL-6 | 25-26 | 1300005424 | 2025-09-02 | 217045 | 0 |  | 217045 | 217045 | 2025-10-08 | [6 empty] | 194855 | 17800 | [7 empty] | 212655 | 97.9774 | 4390 |  |  | Completed
31 | OMAXE (Hazratganj-Lacknow) | 25-26 | OML/R5L/11011203477 | 2025-09-03 | 737756 | 0 |  | 737756 | 737756 | 2025-11-11 | [15 empty] | 0 | 0 | 737756 |  |  | RA-01st Done, Invocie to be Raise.
54 | PSM ENTERPRISES | Tally | PSM/BMS/AMRT/25-26/001 | 2025-08-11 | 50000 | 0 |  | 50000 | 50000 | [6 empty] | 50000 | [9 empty] | 50000 | 100 | 0
32 | RELAXO -AMC | Tally | 2300018318 | 2025-09-19 | 2839930 | 0 |  | 2839930 | 2839930 | [6 empty] | 709982.5 |  | 709983 | [7 empty] | 1419965.5 | 50 | 1419964.5
33 | OMAXE (Bahadur Garh) | 25-26 | 11011204044 | 2025-09-23 | 1694224 | 0 |  | 1694224 | 1694224 | 2025-11-20 | [8 empty] | 299838 | [6 empty] | 299838 | 17.6977 | 1394386 |  |  | Invoice raised as on 18-12-2025
34 | OMAXE (Chandigarh-Isabela) | 25-26 | 11044135650 | 2025-09-23 | 289083 | 0 |  | 289083 | 289083 | [16 empty] | 0 | 0 | 289083
35 | OMAXE (Chandigarh-Emred-C) | 25-26 | 11044135651 | 2025-09-23 | 289083 | 0 |  | 289083 | 289083 | [16 empty] | 0 | 0 | 289083
36 | Nipl Panipat-CCTV | 25-26 | Final | 2025-10-13 | 9850000 | 0 |  | 9850000 | 9850000 | 2025-12-19 | [8 empty] | 1031222 | [6 empty] | 1031222 | 10.4693 | 8818778
37 | Vishal Infra-November | 25-26 | Final | 2025-10-15 | 2829825 | 0 |  | 2829825 | 2829825 | [16 empty] | 0 | 0 | 2829825
38 | Vishal Infra-Oscar | 25-26 | Final | 2025-10-11 | 2829825 | 0 |  | 2829825 | 2829825 | 2025-12-06 | [15 empty] | 0 | 0 | 2829825 |  |  | RA-01st is done, Invoice to be raise-Pending cleint side.
39 | SPG-ITO-Control Module | 25-26 |  | 2025-11-19 | 249000 | 0 |  | 249000 | 249000 | 2025-11-29 | [8 empty] | 211650 | [6 empty] | 211650 |  | 37350
| AIM Power-Cornerwalk | 25-26 |  | 2025-12-23 | 253705 | 0 |  | 253705 | 253705 | 2025-12-31 | [8 empty] | 253705 | [6 empty] | 253705 |  | 0 |  |  | Po Completed
| I-Thum-Solutrean Building | 25-26 |  | 2025-12-30 | 5820332 | 0 |  | 5820332 | 5820332
0
Grand Total |  |  |  |  | 287785612 | 93132548.8 | 109343401.2 | 88969447 | 198312848.2 |  | 1453395 | 10978461 | 6730463 | 10610813.75 | 9405459.5 | 12804524.5 | 2964927 | 11293980.35 | 5873635 | 1082425 | 329278 | 382493 | 0 | 876877.35 | 85705 | 69358880.75 | 3327.3515 | 123133635.45
Total Billing Booked on Tally till 31-12-2025. | [10 empty] | 72115659.1
Less: Credit Note | [10 empty] | 2756778.35
As per Tally and Working Matched, this is Final Sales Till-30-11-25 | [10 empty] | 69358880.75
(FY.25-26) Month Wise Billing details as per Tally & GST Portal wise
[8 empty] | Sr.No. | Month |  | amount | Remarks
[8 empty] | 1 | Apr'25 |  | 1453395 | Tally Matched as per Cal sheet
[8 empty] | 2 | May'25 |  | 10978461 | Tally Matched as per Cal sheet
[6 empty] | 0 |  | 3 | Jun'25-Delhi |  | 6605463 | Tally Matched as per Cal sheet | June Total-6730463
[8 empty] | 3 | Jun'25UP-Tally-Jun |  | 125000 | Add Embrace in UP Branches rs.125000/-
[8 empty] | 4 | Jul'25 |  | 10610813.75 | Tally Matched as per Cal sheet
Admin Po Value | [7 empty] | 5 | Aug'25 |  | 9405459.5 | Tally Matched as per Cal sheet
[8 empty] | 6 | Sep'25 |  | 12804524.5 | Tally Matched as per Cal sheet
[8 empty] | 7 | Oct'25. |  | 2964927 | Tally Matched as per Cal sheet
[8 empty] | 8 | Nov'25 |  | 11293980.35 | Tally Matched as per Cal sheet
Less | [11 empty] | Tally Matched as per Cal sheet
Finla | [7 empty] | 9 | Dec'25 |  | 5873635 | Tally Matched as per Cal sheet
[8 empty] | Total |  |  | 72115659.1 | Tally matched as Cal. sheet
Non Po | [7 empty] | Less Credit Note till Dec'25 |  |  | 2756778.35 | -
[8 empty] | Final Sales |  |  | 69358880.75 | till Nov_ tally Matched as on 30-11-25
[8 empty] | Final Sales Summary | Up Tally |  | Delhi Tally | Total Sales Till Dec'2025
[9 empty] | 125000 |  | 69233880.75 | 69358880.75
Summary
Installation (MB) billing as on 31-12-25 for party Wise FY-25-26
[8 empty] | Sr.No. | Project |  | Amount | Remarks
[8 empty] | 1 | Grandthum |  | 150731
[8 empty] | 2 | AB Mauri |  | 203432
[8 empty] | 3 | Max Mohali |  | 120986
[8 empty] | 4 | Max Saket |  | 228365
[8 empty] | 5 | Crystaltown |  | 98760
[8 empty] | 6 | SCO-113 |  | 142573 | still handing over Pending as well as RA Bill pending from cleint side
[8 empty] | 7 | Panipat-Old |  | 67050 | Dec'25
[8 empty] | 8 | Nilp-Boom Barrier |  | 177552 | Dec'25
[8 empty] | 9 | Cornerwalk |  | 123170 | Dec'25
[8 empty] | Total Value of MB |  |  | 1312619
[8 empty] | Total Value of Supply |  |  | 68046261.75
[8 empty] | Total Billing as of now-31-12-25 |  |  | 69358880.75

## Till-Nov Billing
Summary of Old & New PO Balance, & FY25-26 Billing Details
Billing Details (FY_2025-26) Reporting date:30-11-2025
Total> |  |  |  | 281757875 | 93007548.8 | 109343401.2 | 82678774 | 192022175.2 | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Credit Note | Credit Note | Credit Note | Credit Note | Credit Note | Total Billing (F.Y.25-25) till 30-11-2025 | Bill in FY-24-25 | FY 24-25 & 25-26 | Report till 29-10-2025.
Sr.No. | Cleint's Name | PO Number | PO Date will be fill | PO Value | Bill till FY-24-25 | OLD PO Balance | PO Value (25-26) | Total PO Value in hand | Apr'2025 | May'2025 | Jun'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Total Billing_as of now after less Credit Note | Apr'24 to Mar'25 | Total Billing | Billing Type | Project Head Name | Remarks
1 | Angel Hyaat |  |  | 1859780 | 1574780 | 285000 | 0 | 285000 | 0 | [12 empty] | 0 | 1574780 | 1574780 |  | Satish Ji
2 | Krihsna Aiims |  |  | 12281602 | 1260654 | 11020948 | 0 | 11020948 | 0 |  |  | 441466.9 | [9 empty] | 441466.9 | 1260654 | 1702120.9 |  | Satish Ji
3 | Trump Tower |  |  | 480000 | 363200 | 116800 | 0 | 116800 | 0 | [12 empty] | 0 | 363200 | 363200 |  | Mahipal
4 | SCO-113 Lekh |  |  | 1675761 | 1023779.3 | 651981.7 | 473318 | 1125299.7 | 0 |  |  |  |  | 340990 |  | 416432 |  |  |  |  | 282440 | 474982 | 1023779.3 | 1498761.3 |  | Mahipal
5 | M3M R& R |  |  | 11734161 | 1037342.5 | 10696818.5 | 0 | 10696818.5 | 0 |  |  | 1025696 | [9 empty] | 1025696 | 1037342.5 | 2063038.5 |  | Mahipal
6 | M3M-Panipat-Old |  |  | 2468800 | 735280 | 1733520 | 0 | 1733520 | 0 | [6 empty] | 785680 | [5 empty] | 785680 | 735280 | 1520960 |  | Mahipal |  | 125780151.1
7 | Blue Star-AB Mauri |  |  | 6925030 | 3262387 | 3662643 | 2438531 | 6101174 | - | - | 974211 | 203431.85 |  |  |  | 1668274 | 8283 |  |  |  |  | 2837633.85 | 3262387 | 6100020.85 |  | Satish
8 | M3M JEWEL - Music System |  |  | 1126004 | 0 | 1126004 | 0 | 1126004 | 0 |  |  |  |  | 114450 | [7 empty] | 114450 | 0 | 114450 |  | Mahipal
9 | M3M -Paragon - Music System |  |  | 3699991 | 0 | 3699991 | 0 | 3699991 | 0 |  |  |  |  | 267050 | [7 empty] | 267050 | 0 | 267050 |  | Mahipal
10 | M3M -Jewel Security System | Lekh/Jewel 25/Security System and Access Control Work/LOA/2025/26 |  | 2832390 | 0 | 2832390 | 0 | 2832390 | 0 |  |  |  | 158790 | 110642 |  | 271985 |  |  | 158790 |  |  | 382627 | 0 | 382627 | Supply | Mahipal | RA-01st Invoice to be raise
11 | M3M -Paragon-57 Security System | Paryapt/Paragon-57/Security System and Access Control Work/LOA/2025/81 |  | 4100000 | 0 | 4100000 | 0 | 4100000 | 0 |  |  |  | 223703 | 152303 |  | 283010 |  |  | 223703 |  |  | 435313 | 0 | 435313 | Supply | Mahipal | RA-01st Invoice to be raise
12 | M3M -Corner Walk-Prompt-CCTV | Prompt/Corner Walk/SITC/of CCTV Work for Loft Area/LOA/2024/343 |  | 922583 | 0 | 0 | 922583 | 922583 | 0 | 0 |  |  | 413295 | 208538 | [7 empty] | 621833 | 0 | 621833 |  | Mr Pooran
13 | Labotek GGIPU |  |  | 907796 | 0 | 907796 | 0 | 907796 | 0 | 427607 |  | 333718 | [9 empty] | 761325 | 0 | 761325 |  | Mr Prakash
14 | Power House Jhajjar |  |  | 780500 | 205595 | 574905 | 0 | 574905 | 130500 | [12 empty] | 130500 | 205595 | 336095 |  | Ashu | Completed "The payment is still pending
13 | SPG-ITO Mumbai-ELV |  |  | 6100585 | 3683520 | 2417065 | 0 | 2417065 |  |  | 1443970 | 576963 |  |  |  | 170107 | [5 empty] | 2191040 | 3683520 | 5874560 |  | Satish Ji & Vijay | Invoice to be raise
14 | SPG-ITO Mumbai-BMS |  |  | 6350710 | 3293305 | 3057405 | 0 | 3057405 | 0 | 510195 | 203362 | 266912 |  | 79040 |  | 50620 | [5 empty] | 1110129 | 3293305 | 4403434 | Supply | Satish Ji & Pooran | Invoice to be raise
15 | MRC-Jammu |  |  | 3114148 | 1296490 | 1817658 | 0 | 1817658 | 695175 | [12 empty] | 695175 | 1296490 | 1991665 | Supply | Satish Ji | Invoice raised.
18 | RFL-AMC-Q4 |  |  | 2750000 | 2062500 | 687500 | 0 | 687500 |  | 687500 | [11 empty] | 687500 | 2062500 | 2750000 |  | Sayed & Sandeep | PO Completed
16 | AL SOFTWEB - Grandthum_CCTV Bhutani Group |  |  | 31196662 | 7470651 | 23726011 | 0 | 23726011 | 0 | 1254829 | 2017195 |  | 0 | 1709426 | 742587 |  |  |  | 0 |  |  | 5724037 | 7470651 | 13194688 |  | Pooran Ji | RA-05th is done Invoice to be raise
17 | RIC-Eco Park |  |  | 73000000 | 44279628 | 28720372 | 0 | 28720372 |  |  |  |  | 411862.5 | 1984800 |  | 395831 | [5 empty] | 2792493.5 | 44279628 | 47072121.5 |  | Pooran Ji | PI Raises
20 | SPG-Hanumnagarh |  |  | 20680085 | 16246740 | 4433345 | 0 | 4433345 |  |  |  | 4433345 | [9 empty] | 4433345 | 16246740 | 20680085 |  | Pooran Ji | Completed
21 | NCDC-Dyna Filters-ELV |  |  | 3018195 | 2317975 | 700220 | 0 | 700220 | [13 empty] | 0 | 2317975 | 2317975 |  | Satish Ji
22 | NCDC-Dyna Filters-BMS |  |  | 5232770 | 2902732 | 2330038 | 0 | 2330038 | [13 empty] | 0 | 2902732 | 2902732 |  | Satish Ji
18 | Max Saket-Delhi- BMS-Hitachi |  |  | 10788650 | 0 | 0 | 10788650 | 10788650 | 0 | 3385398 | 583224 | 11281 | 550862 | 185914 |  | 723777 | 583224 |  |  |  | 185914 | 4671318 | 0 | 4671318 | Supply | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
19 | Max-Mohali- Acces Control Ahluwalia |  |  | 5232900 | 0 | 0 | 5232900 | 5232900 | - | 1376859 | 300933 |  | 219678 | 1934090 |  | 347980 | [5 empty] | 4179540 | 0 | 4179540 |  | Mr Pooran | RA5th_ Done Invocie to be raise
20 | Max-Mohali-BMS-Hitachi |  |  | 5247334 | 0 | 0 | 5247334 | 5247334 | - | 2191333 | 490918 |  | 625792 | 567165 |  | 208134 | 490918 |  |  |  |  | 3592424 | 0 | 3592424 |  | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
21 | Central Park-Old |  |  | 2728200 | 0 | 0 | 2728200 | 2728200 | [5 empty] | 236577 |  | 840924 | [5 empty] | 1077501 | 0 | 1077501 |  | Mahipal
27 | Nestle AMC for 2 Site Patna & Serampore |  |  | 230765 | 0 | 0 | 230765 | 230765 | 55100 | -55000 | [11 empty] | 100 | 0 | 100 |  | Sandeep Kaur | SES Pending Cancelled this PO
22 | Hari Electric Work | 0 |  | 10920 | 0 | 0 | 10920 | 10920 | 10920 | 0 | 0 | [10 empty] | 10920 | 0 | 10920 |  |  | Completed
28 | Nestle Bhiwandi |  |  | 17990 | 0 | 17990 | 0 | 17990 | 17990 | [12 empty] | 17990 | 0 | 17990 |  | Sandeep Kaur | Completed
29 | Nestle Ponda-Goa |  |  | 17990 | -9010 | 27000 | 0 | 27000 | 27000 | 0 | [11 empty] | 27000 | -9010 | 17990 |  | Ashu | Completed
30 | Labotek GGIPU |  |  | 184741 | 0 | 0 | 184741 | 184741 | 156460 | 0 | [11 empty] | 156460 | 0 | 156460 |  | Mr Prakash
31 | Leighton Contactors |  |  | 1873300 | 0 | 0 | 1873300 | 1873300 | 360250 | 936650 | 576400 | [10 empty] | 1873300 | 0 | 1873300 |  | HSS | Completed
32 | Angel-Ramai-Haryana | Against V9's Quote |  | 263090 | 0 | 0 | 263090 | 263090 | 0 | 263090 | [11 empty] | 263090 | 0 | 263090 |  | Sanjay | Completed
33 | Embrace Infrasys | EIPL-PO-252606 |  | 125000 | 0 | 0 | 125000 | 125000 |  | 0 | 125000 | [10 empty] | 125000 | 0 | 125000 |  |  | Completed
22 | Grandthum-Access Control | ALSPL/V9/SB/25- 26/WO/-8 |  | 8005040 | 0 | 0 | 8005040 | 8005040 |  |  |  | 3079200 |  | 3869952 | [7 empty] | 6949152 | 0 | 6949152
35 | DPS School |  |  | 1050457 | 0 | 0 | 1050457 | 1050457 |  |  |  |  | 1078161 |  |  |  |  | 329278 |  |  |  | 748883 | 0 | 748883 |  |  | PI Prepare Bill to be raise on Jul'25 MB Verifcation is pending from Pooran
36 | Marada-Nestle Serampore-Service Call | - |  | 10000 | 0 | 0 | 10000 | 10000 |  |  | 10000 | [10 empty] | 10000 | 0 | 10000 |  |  | Completed
37 | GVD-Switch Billing | - |  | 197750 | 0 | 0 | 197750 | 197750 |  |  | 5250 | 192500 | [9 empty] | 197750 | 0 | 197750 |  |  | Completed
23 | STERLING-Max Gurgaon | 4900000812 |  | 7400000 | 0 |  | 7400000 | 7400000 | [7 empty] | 1816482 | [5 empty] | 1816482 | 0 | 1816482
25 | Nestle Raipur- Paid Service | 4561970433 |  | 10000 | 0 |  | 10000 | 10000 | [13 empty] | 0 | 0 | 0
26 | Nestle Kheda-Paid | 4561931385 |  | 20000 | 0 |  | 20000 | 20000 | [13 empty] | 0 | 0 | 0
24 | Nestle (Ganaur) | 4561964158 |  | 1430300 | 0 |  | 1430300 | 1430300 | [6 empty] | 1430300 | [6 empty] | 1430300 | 0 | 1430300 |  |  | Completed
28 | Avl India Pvt ltd | 40375984 |  | 148000 | 0 |  | 148000 | 148000 |  |  |  |  | 74000 | [8 empty] | 74000 | 0 | 74000
29 | Olive karoke | Music System |  |  | 0 |  | 360000 | 360000 | [13 empty] | 0 | 0 | 0
25 | Nipl Panipat | UTTIRNA/PANIPAT PH-2/SITC Of Automatic BoomBarrier/LOA/2025/68 |  | 10389046 | 0 |  | 10389046 | 10389046 |  |  |  |  | 5649316 | 283605 |  | 1692151 | [5 empty] | 7625072 | 0 | 7625072 |  |  | Ra done Materil to be deliver
45 | Pixel Info | Return |  | 46300 | 0 |  | 46300 | 46300 |  |  |  | 46300 | [9 empty] | 46300 | 0 | 46300 |  |  | Done
26 | Crystaltown_New | 2000003682, Date:21-08-2025 |  | 639823 | 0 |  | 639823 | 639823 | [6 empty] | 153540 | 894810.35 |  |  |  |  | 408523.35 | 639827 | 0 | 639827 |  |  | Completed
47 | RELAXO RFL-6 (Service) | 2300018047 |  | 31480 | 0 |  | 31480 | 31480 | [13 empty] | 0 | 0 | 0
48 | RELAXO RFL- 9 (Service) | 2300018052 |  | 18550 | 0 |  | 18550 | 18550 | [13 empty] | 0 | 0 | 0
49 | RELAXO RFL- 9 (Service) | 2300018053 |  | 59980 | 0 |  | 59980 | 59980 | [13 empty] | 0 | 0 | 0
27 | RELAXO RFL - 9 (Supply) | 1300005422 |  | 331415 | 0 |  | 331415 | 331415 | [6 empty] | 308865 | [6 empty] | 308865 | 0 | 308865 |  |  | Completed
28 | RELAXO -MD House RK Dua |  |  | 16490 | 0 |  | 16490 | 16490 | [6 empty] | 16490 | [6 empty] | 16490 | 0 | 16490 |  |  | Completed
29 | RELAXO RFL - 9 (Supply) | 1300005423 |  | 119040 | 0 |  | 119040 | 119040 | [6 empty] | 118290 | [6 empty] | 118290 | 0 | 118290 |  |  | Completed
30 | RELAXO RFL-6 (Supply) | 1300005424 |  | 217045 | 0 |  | 217045 | 217045 | [6 empty] | 194855 | 17800 | [5 empty] | 212655 | 0 | 212655 |  |  | Completed
31 | OMAXE (Hazratganj-Lacknow) | OML/R5L/11011203477 |  | 737756 | 0 |  | 737756 | 737756 | [13 empty] | 0 | 0 | 0
54 | PSM ENTERPRISES | PSM/BMS/AMRT/25-26/001 |  | 50000 | 0 |  | 50000 | 50000 | [5 empty] | 50000 | [7 empty] | 50000 | 0 | 50000
32 | RELAXO -AMC | 2300018318 |  | 2839930 | 0 |  | 2839930 | 2839930 | [5 empty] | 709982.5 |  | 709983 | [5 empty] | 1419965.5 | 0 | 1419965.5
33 | OMAXE (Bahadur Garh) | 11011204044 |  | 1694224 | 0 |  | 1694224 | 1694224 | [13 empty] | 0 | 0 | 0
34 | OMAXE (Chandigarh-Isabela) | 11044135650 |  | 289083 | 0 |  | 289083 | 289083 | [13 empty] | 0 | 0 | 0
35 | OMAXE (Chandigarh-Emred-C) | 11044135651 |  | 289083 | 0 |  | 289083 | 289083 | [13 empty] | 0 | 0 | 0
36 | Nipl Panipat-CCTV | Final |  | 9850000 | 0 |  | 9850000 | 9850000 | [13 empty] | 0 | 0 | 0
37 | Vishal Infra-November | Final |  | 2829825 | 0 |  | 2829825 | 2829825 | [13 empty] | 0 | 0 | 0
38 | Vishal Infra-Oscar | Final |  | 2829825 | 0 |  | 2829825 | 2829825 | [13 empty] | 0 | 0 | 0
39 | SPG-ITO-Control Module |  |  | 249000 | 0 |  | 249000 | 249000 | [13 empty] | 0 | 0 | 0
Grand Total |  |  |  | 281757875 | 93007548.8 | 109343401.2 | 82678774 | 192022175.2 | 1453395 | 10978461 | 6730463 | 10610813.75 | 9405459.5 | 12804524.5 | 2964927 | 11293980.35 | 1082425 | 329278 | 382493 | 0 | 876877.35 | 63570950.75 | 93007548.8 | 156578499.55
Total Billing Booked on Tally till 30-11-2025. | [8 empty] | 66242024.1
Less: Credit Note | [8 empty] | 2671073.35
As per Tally and Working Matched, this is Final Sales Till-30-11-25 | [8 empty] | 63570950.75
Final Month Wise Billing details as per Tally Acts.
[7 empty] | Sr.No. | Month | amount | Remarks
[7 empty] | 1 | Apr'25 Tally billing amt | 1453395 | Tally Matched as per Cal sheet
[7 empty] | 2 | May'25 Tally billing amt | 10978461 | Tally Matched as per Cal sheet
[5 empty] | 0 |  | 3 | Jun'25-Delhi Tally billing amt Till 26-06-25 | 6605463 | Tally Matched as per Cal sheet | June Total-6730463
[7 empty] | 3 | UP-Tally-Jun | 125000 | Add Embrace in UP Branches rs.125000/-
[6 empty] | Nilp | 4 | Jul'25 Tally billing amt | 10610813.75 | Tally Matched as per Cal sheet
Admin Po Value | [6 empty] | 5 | Aug'25-till 20-08-25 Tally billing amt | 9405459.5 | Tally Matched as per Cal sheet
[7 empty] | 6 | Sep'25-till 30-09-25 Tally billing amt | 12804524.5 | Tally Matched as per Cal sheet
[7 empty] | 7 | Oct'25-till 31.-10-25 Tally billing amt | 2964927 | Tally Matched as per Cal sheet
[7 empty] | 8 | Oct'25-till 30-11-25 Tally billing amt | 11293980.35 | Tally Matched as per Cal sheet
Less
Finla | [6 empty] | Total |  | 66242024.1 | Tally matched as Cal. sheet
[7 empty] | Less Credit Note on Nov'25 |  | 2671073.35 |  | Up Tally | Delhi Tally | Remarks
[7 empty] | Final Sales |  | 63570950.75 | till Nov_ tally Matched as on 30-11-25 | 125000 | 63445950.75 | Matched-30-11-25
Non Po | [23 empty] | Summary
Installation (MB) billing as on 30-11-25 for party Wise FY-25-26
Sr.No.
1
2
3
4
5
6
Total Value of MB
Total Value of Supply
Total Billing as of now-30-11-25

## Month-wise billing-MIS
Month-wise Billing MIS Report-2025
(2025-26) Month Wise Billing detailsas per Tally & GST Portal wise
Sr.No. | Month | amount | Remarks
1 | Apr'25 | 1453395 | Tally Matched as per Cal sheet
2 | May'25 | 10978461 | Tally Matched as per Cal sheet
3 | Jun'25-Delhi | 6605463 | Tally Matched as per Cal sheet
3 | Jun'25UP-Tally-Jun | 125000 | Add Embrace in UP Branches rs.125000/-
4 | Jul'25 | 10610813.75 | Tally Matched as per Cal sheet
5 | Aug'25 | 9405459.5 | Tally Matched as per Cal sheet
6 | Sep'25 | 12804524.5 | Tally Matched as per Cal sheet
7 | Oct'25. | 2964927 | Tally Matched as per Cal sheet
8 | Nov'25 | 11293980.35 | Tally Matched as per Cal sheet
9 | Dec'25 | 5873635 | Tally Matched as per Cal sheet
Total |  | 72115659 | Tally matched as Cal. sheet
Less Credit Note till Dec'25 |  | 2756778 | -
Final Sales |  | 69358881 | till Nov_ tally Matched as on 30-11-25