## Old Working
PO VALUE MONTH WISE- 2024-25
Ref.no | S.no | PO DATE | Month | PO NUMBER | PARTY NAME | PO VALUE | Billing Date | Billing Value | Gap Period against PO Date | Invoice Type | PO Balance | STATUS-PENDING/COMLETED
239 | 1 | 16-04-2024 | Apr | Rajbagh / MUSIC SYSTEM/18 | ANGEL EXPANDERS PRIVATE LIMITED | 1046510 | 2024-09-05 | 512736 | 142 | Supply | 184802 | Pending
[7 empty] | 2025-02-16 | 348972 | 306 | Installation
239 | 1 | 16-04-2024 | Apr | Rajbagh / FAS SYSTEM/18 | ANGEL EXPANDERS PRIVATE LIMITED | 795840 | 2024-09-05 | 511824 | 142 | Supply | 105425 | Pending
[7 empty] | 2025-02-13 | 178591 | 303 | Installation
210 | 2 | 22-05-2024 | May | 4559986529 | Nestle-Haridwar | 47200 | 2024-06-10 | 47200 | 19 | Installation | 0 | Completed
212 | 3 | 2024-05-23 |  | 4559998734 | Nestle India Ltd ( Farukh Nagar) | 54000 | 2024-06-13 | 54000 | 21 | Supply | 0 | Completed
274 | 4 | 23-05-2024 |  | KC/SER.AIIMS/103 | AIIMS-Krishna-LV | 12281602 | 2024-10-23 | 654374 | 153 | Supply | 11020948 | Pending
[7 empty] | 2024-12-31 | 606280 | 220 | Supply
275 | 5 | 25-05-2024 |  | KC/SER.AIIMS/113 | AIIMS-Krishna-IT | 17800474 |  | 0 | 0 | 0 | 17800474 | Cancelled
213 to 238,241 to263 | 6 | 2024-06-17 | Jun | 1300003773 | Relaxo Control Room Shifting | 2315061 | 2024-07-31 | 2313680 | 44 | Supply & Services | 1381 | Completed
208 | 7 | 19-06-2024 |  | Trump Tower | Olive Realocon | 480000 | 2024-08-28 | 190400 | 70 | Supply | 116800 | Pending
[7 empty] | 2025-02-27 | 134400 | 253 | Supply
[7 empty] | 2025-03-31 | 38400 | 285 | Installation
240 | 9 | 26-06-2024 |  | 4560159303 | Nestle India Ltd DC Banthara | 2865500 |  |  |  |  | 0
267 | 10 | 2024-01-07 | Jul | 1800001094 | VoLtas-192 Part-B | 12000000 | 2024-08-22 | 2500000 | 228 | Supply | 0 | Completed
[7 empty] | 2024-08-24 | 6500000 | 230 | Supply
[7 empty] | 2024-08-17 | 3000000 | 223 | Supply
264 | 11 | 2024-03-07 |  | SPG/WO/Income tax Building Mumbai/2024-25/001 | SPG-ITO Mumbai-LV | 6100585 | 2025-03-08 | 2634771 | 366 | Supply | 2417065 | Pending
[7 empty] | 2025-03-11 | 1048749 | 369 | Supply
|  | 2024-11-18 |  | SPG/WO/Income tax Building Mumbai/2024-25/001/RA | SPG-ITO Mumbai-BMS | 6050710 | 2025-03-08 | 2993305 | 110 | Supply | 3057405 | Pending
270 | 12 | 2024-07-11 |  | 4560219519 | Nestle-Murthal | 15000 | 2025-10-23 | 15000 | 469 | Service | 0 | Completed
271 | 13 | 2024-07-11 |  | LEK/SCO-113/CCTV Boom Barrier/LOA/2024/91 | M3M Market SCO-113 | 1675761 | 2024-09-30 | 741339.3 | 81 | Supply | 651981.7 | Pending
[7 empty] | 2025-03-05 | 282440 | 237 | Installation
211-A | 14 | 15-07-2024 |  | 7100049106 | Hero Motors. | 1144599 | 2024-07-30 | 1144599 | 15 | Supply | 0
269 | 15 | 16-07-2024 |  | 4700000586 | Bluestar - AB Mauri | 6925030 | 2025-02-15 | 3262387 | 214 | Supply | 3662643 | Pending
272 | 16 | 16-07-2024 |  | Union/Capital-113/PH-2/Security System/LOA/2024/59 | M3M Retail & Residencial-113 | 11734161 | 2025-01-23 | 940517.5 | 191 | Supply | 10696818.5 | Pending
[7 empty] | 2025-03-25 | 96825 | 252 | Installation
211-B | 17 | 17-07-2024 |  | 7100049190 | Hero Motors. | 4649 | 2024-08-01 | 4649 | 15 | Supply | 0 | Completed
273 | 18 | 19-07-2024 |  | UTTIRNA/DDJAY PH-1/Plotted Dev BoomBarrier Work/LOA/2024/43 | M3M Panipat Project | 2468800 | 2024-11-14 | 735280 | 118 | Supply | 1733520 | Pending
268-A | 19 | 26-07-2024 |  | PES/PO/281/2024-25 | AIIMS Trauma Centre | 53000 | 2024-08-30 | 53000 | 35 | Suppy | 0 | Completed
276 | 21 | 2024-08-08 | Aug | 4560364062 | Nestler-Haridwar | 77000 | 2024-08-21 | 59000 | 13 | Supply | 0 | Completed
[7 empty] | 2025-03-21 | 18000 | 225 | Service
277 | 22 | 14-08-2024 |  | 4560370288 | Nestle Ranchi | 30000 | 2024-12-09 | 30000 | 117 | Supply | 0 | Completed
279 | 23 | 17-08-2024 |  | TFSPL/PO/2023-24/281 | 24 Systems | 9999860 | 2024-09-06 | 5400860 | 20 | Supply | 0 | Completed
[7 empty] | 2024-10-25 | 4599000 | 69 | Supply
280 | 24 | 2024-10-09 | Sep | 2000000970 | Relaxo Service Order Of AMC | 2750000 | Aug24 to Feb25 | 2062500 | - | Service | 687500 | Pending
281 | 25 | 13-09-2024 |  | PES/PO/311/2024-25 | PES Installations Pvt. Limited | 55000 | 2024-09-25 | 55000 | 12 | Supply | 0 | Completed
282 | 26 | 25-09-2024 |  | 4560573938 | Nestle-Ponda | 156000 | 2024-10-07 | 156000 | 12 | Supply | 0 | Completed
283 | 27 | 15-10-2024 | Oct | 4560660328 | Nestle-Bhiwandi | 2190650 | 2024-12-09 | 1975650 | 55 | Supply | 0 | Completed
[7 empty] | 2024-12-09 | 215000 | 55 | Service
285 | 28 | 15-10-2024 |  | 4560670686 | Nestle-Ponda | 1949400 | 2024-10-26 | 1264400 | 11 | Supply | 27000 | Pending
[7 empty] | 2025-02-25 | 658000 | 133 | Supply
284 | 29 | 17-10-2024 |  | PES/PO/336/2024-25 | PES Installations Pvt. Limited | 22500 | 2024-10-18 | 22500 | 1 | Supply | 0 | Pending
286 | 30 | 23-10-2024 |  | IDPO00305 | NCC -IIT Delhi | 17700 | 2024-11-09 | 15000 | 17 | Supply | 0 | Pending
287 | 31 | 2024-11-11 | Nov | 24800733 | Seamless Infotech- OP Jindal | 720000 | 2024-11-22 | 166400 | 11 | Supply | 0 | Completed
[7 empty] | 2024-11-30 | 210000 | 19 | Supply
[7 empty] | 2025-02-17 | 343600 | 98 | ITC
288 | 32 | 2024-12-02 |  | SVS/2024-25/099 | SVS Buildwell Pvt Ltd | 333409 | 2024-12-02 | 176800 | 0 | Supply | 156609 | Pending
289-A | 33 | 28-11-2024 |  | ALSPL/V9 TECH/CCTV/2024mdb-323 | AL SOFTWEB - Bhutani Group | 31196662 | 2025-01-16 | 2621962 | 49 | Supply | 23726011 | Pending
[7 empty] | 2025-02-17 | 412214 | 81 | Supply
[7 empty] | 2025-03-30 | 4436475 | 122 | Supply
278 | 34 | 2024-09-12 | Dec | MRC/PO/RI-313 | MRC -Jammu | 3114148 | 2025-01-23 | 1296490 | 133 | Supply | 1817658 | Pending
290 | 36 | 24-12-2024 |  | No.F:GGSIPU/UWD/2024/236 | Labotek -Dwarka | 1150000 | 2025-03-18 | 242204 | 84 | Supply | 907796 | Pending
291 | 37 | 2025-04-01 | Jan | LT/00859/2024-25/S/T2 | Labotek -Noida | 14000 | 2025-01-04 | 14000 | 0 | Supply | 0 | Completed
293 | 38 | 2025-12-01 |  | 1800001320 | TP-Solar BMS Cable | 4571640 | 2025-01-22 | 4571640 | 10 | Supply | 0 | Completed
292 | 39 | 13-01-2025 |  | 4561036685 | Nestle-Serampore | 40000 | 2025-01-09 | 40000 | 4 | Supply | 0 | Completed
294 | 40 | 20-01-2025 |  | Lekh/Jewel25/Music System Work/LOA/2025/25 | M3M JEWEL -Music System | 1126004 | 2026-01-30 | 0 | 375 |  | 1126004 | Pending
295 | 41 | 20-01-2025 |  | Paryapt/Paragon57/Music System Work/LOA/2025/79 | M3M -Paragon -Music System | 3699991 | 2026-01-30 | 0 | 375 |  | 3699991
297 | 42 | 22-01-2025 |  | Lekh/Jewel25/Security System & Access Control Work/LOA/2025/26 | M3M -Jewel Security System | 2832390 | 2026-01-30 | 0 | 373 |  | 2832390
296 | 43 | 14-02-2025 | Feb | Paryapt/Paragon57/Security System & Access Control Work/LOA/2025/81 | M3M -Paragon-57 Security System | 4100000 | 2026-01-30 | 0 | 350 |  | 4100000
298-A | 44 | 14-02-2025 |  | LP/0010/2024-25/W/T2 | Power House-Aiims Jhajhar | 650000 | 2025-03-18 | 650000 | 32 |  | 0 | Completed
299 | 45 | 2025-04-03 | Mar | 2300015088 | Relaxo-AMC -Lowa Khurd | 47250 | 2025-03-18 | 47250 | 14 |  | 0 | Completed
298-B | 46 | 2025-09-03 |  | LP/0011/2024-25/W/T2 | Power House-Aiims Jhajhar | 130500 | - | - | - |  | 130500 | Pending
300 | 47 | 2025-11-03 |  | 4561352750 | Nestle-Chennai | 2736450 | 2025-03-13 | 2736450 |  |  | 0 | Pending
Total | [5 empty] | 159569036 | - | 66040113.8 | - | - | 90660722.2 | -
156700836
159569036
2868200

## For Pooran to billing
Project details for ITC-billing OLD & NEW
Total> |  |  | ITC Billing for Month wise | - | Report till 21-05-2025.
Sr.No. | Cleint's Name | PO Number | May'2025 till-21-5-25 | Total | Billing Type | Project Head Name | Remarks
1 | Angel Hyaat |  |  |  |  | Satish Ji
2 | Krihsna Aiims |  |  |  |  | Satish Ji
3 | Trump Tower |  |  |  |  | Mahipal
4 | SCO-113 Lekh |  |  |  |  | Mahipal
5 | M3M R& R |  |  |  |  | Mahipal
7 | M3M JEWEL - Music System |  |  |  |  | Mahipal
8 | M3M -Paragon - Music System |  |  |  |  | Mahipal
9 | M3M -Jewel Security System | Lekh/Jewel 25/Security System and Access Control Work/LOA/2025/26 |  |  |  | Mahipal
10 | M3M -Paragon-57 Security System | Paryapt/Paragon-57/Security System and Access Control Work/LOA/2025/81 |  |  |  | Mahipal
11 | M3M -Corner Walk-Prompt-CCTV | Prompt/Corner Walk/SITC/of CCTV Work for Loft Area/LOA/2024/343 | 0 |  |  | Mahipal
12 | Labotek GGIPU |  |  |  |  | Mr Prakash
13 | SPG-ITO Mumbai-LV |  |  |  |  | Satish Ji & Vijay
14 | SPG-ITO Mumbai-BMS |  |  |  |  | Satish Ji & Vijay
15 | MRC-Jammu |  |  |  |  | Satish Ji
16 | AL SOFTWEB - Bhutani Group |  |  |  |  | Pooran Ji
17 | RIC-Eco Park |  |  |  |  | Pooran Ji
18 | SPG-Hanumnagarh |  |  |  |  | Pooran Ji
19 | NCDC-Dyna Filters-ELV |  |  |  |  | Satish Ji
20 | NCDC-Dyna Filters-BMS |  |  |  |  | Satish Ji
21 | Max Saket-Delhi-BMS |  |  |  |  | Ajay Chauhan
22 | Max Saket-Mohali- Acces Control |  |  |  |  | Mr Vijay
23 | Max Saket-Mohali-BMS |  |  |  |  | Mr Vijay
24 | Central Park |  |  |  |  | Mahipal
25 | Labotek GGIPU-ELV |  | 0 |  |  | Mr Prakash
26 | Grandthum-Access Control | ALSPL/V9/SB/25-26/WO/-8
Grand Total |  |  | 0 | 0
2025-05-20
45
2025-07-04
49797
7299
57096
Formulas:
Project Head Name = G42+[Project Head Name, row above]

## Final Billing det as per Tally
Summary of Old & New PO Balance, FY25-26 Billing Details
Billing Details (FY_2025-26) Reporting date:31-12-2025
Total> | [6 empty] | 109343401.2 | 76986760 | 186330161.2 |  | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Credit Note | Credit Note | Credit Note | Credit Note | Credit Note | Credit Note | Total Billing till 31-12-2025 | Billing_% | 123096285.45 | Report till 31-12-2025.
Sr.No. | Cleint's Name | Project-24-25 & 25-26 | PO Number | PO Date will be fill | PO Value | Bill till FY-24-25 | OLD PO Balance | PO Value (25-26) | Total PO Value in hand | 01st Material Delivery Date | Apr'2025 | May'2025 | Jun'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Dec'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Dec'2025 | as of now after less Credit Note | %tage of PO Value's Billing | PO_Balance in hand | Billing Type | Project Head Name | Remarks
1 | Angel Hyaat | 24-25 |  |  | 1859780 | 1574780 | 285000 | 0 | 285000 |  | 0 | [14 empty] | 0 | 0 | 285000 |  | Satish Ji | full and final Bill for FAS & PA
2 | Krihsna Aiims | 24-25 |  |  | 12281602 | 1260654 | 11020948 | 0 | 11020948 |  | 0 |  |  | 441466.9 | [11 empty] | 441466.9 | 4.0057 | 10579481.1 |  | Satish Ji
3 | Trump Tower | 24-25 |  |  | 480000 | 363200 | 116800 | 0 | 116800 |  | 0 | [14 empty] | 0 | 0 | 116800 |  | Mahipal
4 | SCO-113 Lekh | 24-25 & 25-26 |  |  | 1675761 | 1023779.3 | 651981.7 | 473318 | 1125299.7 |  | 0 |  |  |  |  | 340990 |  | 416432 | [5 empty] | 282440 |  | 474982 | 42.2094 | 650317.7 |  | Mahipal | RA-05th(CCTV Full and Final Biil is done Invoice to be raise
5 | M3M R& R | 24-25 |  |  | 11734161 | 1037342.5 | 10696818.5 | 0 | 10696818.5 |  | 0 |  |  | 1025696 | [11 empty] | 1025696 | 9.5888 | 9671122.5 |  | Mahipal
6 | M3M-Panipat-Old | 24-25 |  |  | 2468800 | 735280 | 1733520 | 0 | 1733520 |  | 0 | [6 empty] | 785680 | 67050 | [6 empty] | 852730 | 49.1907 | 880790 |  | Mahipal | Ra done, Invoice to be raise. | 114214502.1
7 | Blue Star-AB Mauri | 24-25 |  |  | 6925030 | 3262387 | 3662643 | 2438531 | 6101174 |  | - | - | 974211 | 203431.85 |  |  |  | 1668274 | 199014 | 8283 | [5 empty] | 3036647.85 | 49.7715 | 3064526.15 |  | Satish | RA-06th (MB bill to be raise Invoice.
8 | M3M JEWEL - Music System | 24-25 |  |  | 1126004 | 0 | 1126004 | 0 | 1126004 |  | 0 |  |  |  |  | 114450 | [9 empty] | 114450 | 10.1643 | 1011554 |  | Mahipal
9 | M3M -Paragon - Music System | 24-25 |  |  | 3699991 | 0 | 3699991 | 0 | 3699991 |  | 0 |  |  |  |  | 267050 | [9 empty] | 267050 | 7.2176 | 3432941 |  | Mahipal
10 | M3M -Jewel Security System | 24-25 | Lekh/Jewel 25/Security System and Access Control Work/LOA/2025/26 |  | 2832390 | 0 | 2832390 | 0 | 2832390 |  | 0 |  |  |  | 158790 | 110642 |  | 271985 |  |  |  | 158790 |  |  |  | 382627 | 13.509 | 2449763 | Supply | Mahipal | RA-01st Invoice to be raise
11 | M3M -Paragon-57 Security System | 24-25 | Paryapt/Paragon-57/Security System and Access Control Work/LOA/2025/81 |  | 4100000 | 0 | 4100000 | 0 | 4100000 |  | 0 |  |  |  | 223703 | 152303 |  | 283010 |  |  |  | 223703 |  |  |  | 435313 | 10.6174 | 3664687 | Supply | Mahipal | RA-01st Invoice to be raise
12 | M3M -Corner Walk-Prompt-CCTV |  | Prompt/Corner Walk/SITC/of CCTV Work for Loft Area/LOA/2024/343 |  | 922583 | 0 | 0 | 1139219 | 1139219 |  | 0 | 0 |  |  | 413295 | 208538 |  |  | 123170 | [6 empty] | 745003 | 65.3959 | 394216 |  | Mr Pooran
13 | Labotek GGIPU | 24-25 |  |  | 907796 | 0 | 907796 | 0 | 907796 |  | 0 | 427607 |  | 333718 | [11 empty] | 761325 | 83.8652 | 146471 |  | Mr Prakash
14 | Power House Jhajjar | 24-25 |  |  | 780500 | 205595 | 574905 | 0 | 574905 |  | 130500 | [14 empty] | 130500 | 22.6994 | 444405 |  | Ashu | Completed "The payment is still pending
13 | SPG-ITO Mumbai-ELV | 24-25 |  |  | 6100585 | 3683520 | 2417065 | 0 | 2417065 |  |  |  | 1443970 | 576963 |  |  |  | 170107 | [7 empty] | 2191040 | 90.6488 | 226025 |  | Satish Ji & Vijay | Invoice to be raise
14 | SPG-ITO Mumbai-BMS | 24-25 |  |  | 6350710 | 3293305 | 3057405 | 0 | 3057405 |  | 0 | 510195 | 203362 | 266912 |  | 79040 |  | 50620 | [7 empty] | 1110129 | 36.3095 | 1947276 | Supply | Satish Ji & Pooran | Invoice to be raise
15 | MRC-Jammu | 24-25 |  |  | 3114148 | 1296490 | 1817658 | 0 | 1817658 |  | 695175 | [14 empty] | 695175 | 38.2456 | 1122483 | Supply | Satish Ji | Invoice raised.
18 | RFL-AMC-Q4 | 24-25 |  |  | 2750000 | 2062500 | 687500 | 0 | 687500 |  |  | 687500 | [13 empty] | 687500 | 100 | 0 |  | Sayed & Sandeep | PO Completed
16 | AL SOFTWEB - Grandthum_CCTV Bhutani Group | 24-25 |  |  | 31196662 | 7470651 | 23726011 | 0 | 23726011 |  | 0 | 1254829 | 2017195 |  | 0 | 1709426 | 742587 |  |  |  |  | 0 |  |  | 11705 | 5712332 | 24.0762 | 18013679 |  | Pooran Ji | RA-09th done, Invoice to be raise Check and approval pending from Cleint side.
17 | RIC-Eco Park | to old |  |  | 73000000 | 44279628 | 28720372 | 0 | 28720372 | [5 empty] | 411862.5 | 1984800 |  | 395831 | 246862 | [6 empty] | 3039355.5 | 10.5826 | 25681016.5 |  | Pooran Ji | MB RA03rd Bill is Pending due to Client side.
20 | SPG-Hanumnagarh | to old |  |  | 20680085 | 16246740 | 4433345 | 0 | 4433345 |  |  |  |  | 4433345 | [11 empty] | 4433345 | 100 | 0 |  | Pooran Ji | Completed
21 | NCDC-Dyna Filters-ELV | to old |  |  | 3018195 | 2317975 | 700220 | 0 | 700220 | [16 empty] | 0 | 0 | 700220 |  | Satish Ji
22 | NCDC-Dyna Filters-BMS | to old |  |  | 5232770 | 2902732 | 2330038 | 0 | 2330038 | [16 empty] | 0 | 0 | 2330038 |  | Satish Ji
18 | Max Saket-Delhi- BMS-Hitachi | 25-26 |  | 2025-04-01 | 10788650 | 0 | 0 | 10788650 | 10788650 | 2025-04-15 | 0 | 3385398 | 583224 | 11281 | 550862 | 185914 |  | 723777 |  | 583224 |  |  |  | 185914 |  | 4671318 | 43.2984 | 6117332 | Supply | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
19 | Max-Mohali- Acces Control Ahluwalia | 25-26 |  | 2025-04-01 | 5232900 | 0 | 0 | 5232900 | 5232900 | 2025-05-28 | - | 1376859 | 300933 |  | 219678 | 1934090 |  | 347980 | [7 empty] | 4179540 | 79.8704 | 1053360 |  | Mr Pooran | RA5th_ Done Invocie to be raise
20 | Max-Mohali-BMS-Hitachi | 25-26 |  | 2025-04-01 | 5247334 | 0 | 0 | 5247334 | 5247334 | 2025-05-11 | - | 2191333 | 490918 |  | 625792 | 567165 |  | 208134 |  | 490918 | [5 empty] | 3592424 | 68.4619 | 1654910 |  | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
21 | Central Park-Old | 25-26 |  | 2025-04-01 | 2728200 | 0 | 0 | 2728200 | 2728200 | 2025-07-21 | [5 empty] | 236577 |  | 840924 | 134964 | [6 empty] | 1212465 | 44.4419 | 1515735 |  | Pooran Ji | RA-03rd done Invocie to be Raise
27 | Nestle AMC for 2 Site Patna & Serampore | Tally |  | 2025-04-01 | 230765 | 0 | 0 | 230765 | 230765 |  | 55100 | -55000 | [6 empty] | 55000 | [6 empty] | 55100 | 23.8771 | 175665 |  | Sandeep Kaur | SES Pending Cancelled this PO
22 | Hari Electric Work | Tally | 0 |  | 10920 | 0 | 0 | 10920 | 10920 |  | 10920 | 0 | 0 | [12 empty] | 10920 | 100 | 0 |  |  | Completed
28 | Nestle Bhiwandi | Tally |  |  | 17990 | 0 | 17990 | 0 | 17990 |  | 17990 | [14 empty] | 17990 | 100 | 0 |  | Sandeep Kaur | Completed
29 | Nestle Ponda-Goa | Tally |  |  | 17990 | -9010 | 27000 | 0 | 27000 |  | 27000 | 0 | [13 empty] | 27000 | 100 | 0 |  | Ashu | Completed
30 | Labotek GGIPU | Tally |  | 2025-04-01 | 184741 | 0 | 0 | 184741 | 184741 |  | 156460 | 0 | [13 empty] | 156460 | 84.6915 | 28281 |  | Mr Prakash
31 | Leighton Contactors | 25-26 |  | 2025-05-21 | 1873300 | 0 | 0 | 1873300 | 1873300 | 2025-05-03 | 360250 | 936650 | 576400 | [12 empty] | 1873300 | 100 | 0 |  | HSS | Completed
32 | Angel-Ramai-Haryana | Tally | Against V9's Quote | 2025-04-22 | 263090 | 0 | 0 | 263090 | 263090 |  | 0 | 263090 | [13 empty] | 263090 | 100 | 0 |  | Sanjay | Completed
33 | Embrace Infrasys | Tally | EIPL-PO-252606 | 2025-05-15 | 125000 | 125000 | 0 | 125000 | 125000 |  |  | 0 | 125000 | [12 empty] | 125000 | 100 | 0 |  |  | Completed
22 | Grandthum-Access Control | 25-26 | ALSPL/V9/SB/25- 26/WO/-8 | 2025-05-12 | 8005040 | 0 | 0 | 8005040 | 8005040 | 2025-06-11 |  |  |  | 3079200 |  | 3869952 | [9 empty] | 6949152 | 86.8097 | 1055888 |  |  | RA-03rd done Invocie to be Raise on Jan'25
35 | DPS School | 25-26 |  | 2025-05-26 | 1050457 | 0 | 0 | 1050457 | 1050457 | 2025-06-04 |  |  |  |  | 1078161 | [5 empty] | 329278 |  |  |  |  | 748883 | 71.2912 | 301574 |  |  | PI Prepare Bill to be raise on Jul'25 MB Verifcation is pending from Pooran
36 | Marada-Nestle Serampore-Service Call | Tally | - |  | 10000 | 0 | 0 | 10000 | 10000 |  |  |  | 10000 | [12 empty] | 10000 | 100 | 0 |  |  | Completed
37 | GVD-Switch Billing | Tally | - |  | 197750 | 0 | 0 | 197750 | 197750 |  |  |  | 5250 | 192500 | [11 empty] | 197750 | 100 | 0 |  |  | Completed
23 | STERLING-Max Gurgaon | 25-26 | 4900000812 | 2025-07-14 | 7400000 | 0 |  | 7400000 | 7400000 | 2025-11-26 | [7 empty] | 1816482 | 2612420 | [6 empty] | 4428902 | 59.85 | 2971098
25 | Nestle Raipur- Paid Service | Tally | 4561970433 |  | 10000 | 0 |  | 10000 | 10000 | [16 empty] | 0 | 0 | 10000
26 | Nestle Kheda-Paid | Tally | 4561931385 |  | 20000 | 0 |  | 20000 | 20000 | [16 empty] | 0 | 0 | 20000
24 | Nestle (Ganaur) | 25-26 | 4561964158 | 2025-07-17 | 1430300 | 0 |  | 1430300 | 1430300 | 2025-07-29 | [6 empty] | 1430300 | [8 empty] | 1430300 | 100 | 0 |  |  | Completed
28 | Avl India Pvt ltd | 25-26 | 40375984 | 2025-07-18 | 148000 | 0 |  | 148000 | 148000 | 2025-08-05 |  |  |  |  | 74000 |  |  |  | 74000 | [5 empty] | 74000 | 74000 | 50 | 74000
29 | Olive karoke | 25-26 | Music System | 2025-08-18 |  | 0 |  | 360000 | 360000 | 2025-12-23 | [15 empty] | 0 | 0 | 360000 |  |  | RA-01st Done, Invocie to be Raise.
25 | Nilp Panipat-Boom Barrier | 25-26 | UTTIRNA/PANIPAT PH-2/SITC Of Automatic BoomBarrier/LOA/2025/68 | 2025-07-01 | 10389046 | 0 |  | 10389046 | 10389046 | 2025-08-20 |  |  |  |  | 5649316 | 283605 |  | 1692151 | 473280 | [6 empty] | 8098352 | 77.9509 | 2290694 |  |  | Ra done Materil to be deliver
45 | Pixel Info | Tally | Return |  |  | 0 |  | 46300 | 46300 |  |  |  |  | 46300 | [11 empty] | 46300 | 100 | 0 |  |  | Done
26 | Crystaltown_New | 25-26 | 2000003682, Date:21-08-2025 | 2025-08-21 | 639823 | 0 |  | 639823 | 639823 | 2025-09-17 | [6 empty] | 153540 | 894810.35 | [5 empty] | 408523.35 |  | 639827 | 100.0006 | -4 |  |  | Completed
47 | RELAXO RFL-6 | 25-26 | 2300018047 | 2025-09-01 | 31480 | 0 |  | 31480 | 31480 | 2025-12-31 | [8 empty] | 31480 | [6 empty] | 31480 | 100 | 0 |  |  | Completed
48 | RELAXO RFL- 9 | 25-26 | 2300018052 | 2025-09-01 | 18550 | 0 |  | 18550 | 18550 | 2025-10-03 | [15 empty] | 0 | 0 | 18550 |  |  | Completed
49 | RELAXO RFL- 9 | 25-26 | 2300018053 | 2025-09-01 | 59980 | 0 |  | 59980 | 59980 | 2025-12-31 | [8 empty] | 59980 | [6 empty] | 59980 | 100 | 0 |  |  | Completed
27 | RELAXO RFL - 9 | 25-26 | 1300005422 | 2025-09-01 | 331415 | 0 |  | 331415 | 331415 | 2025-10-03 | [6 empty] | 308865 | [8 empty] | 308865 | 93.1958 | 22550 |  |  | Completed
28 | RELAXO -MD House RK Dua | Tally |  |  | 16490 | 0 |  | 16490 | 16490 | [7 empty] | 16490 | [8 empty] | 16490 | 100 | 0 |  |  | Completed
29 | RELAXO RFL - 9 | 25-26 | 1300005423 | 2025-09-01 | 119040 | 0 |  | 119040 | 119040 | 2025-10-08 | [6 empty] | 118290 | [8 empty] | 118290 | 99.37 | 750 |  |  | Completed
30 | RELAXO RFL-6 | 25-26 | 1300005424 | 2025-09-02 | 217045 | 0 |  | 217045 | 217045 | 2025-10-08 | [6 empty] | 194855 | 17800 | [7 empty] | 212655 | 97.9774 | 4390 |  |  | Completed
31 | OMAXE (Hazratganj-Lacknow) | 25-26 | OML/R5L/11011203477 | 2025-09-03 | 737756 | 0 |  | 737756 | 737756 | 2025-11-11 | [15 empty] | 0 | 0 | 737756 |  |  | RA-01st Done, Invocie to be Raise.
54 | PSM ENTERPRISES | Tally | PSM/BMS/AMRT/25-26/001 | 2025-08-11 | 50000 | 0 |  | 50000 | 50000 | [6 empty] | 50000 | [9 empty] | 50000 | 100 | 0
32 | RELAXO -AMC | Tally | 2300018318 | 2025-09-19 | 2839930 | 0 |  | 2839930 | 2839930 | [6 empty] | 709982.5 |  | 709983 | [7 empty] | 1419965.5 | 50 | 1419964.5
33 | OMAXE (Bahadur Garh) | 25-26 | 11011204044 | 2025-09-23 | 1694224 | 0 |  | 1694224 | 1694224 | 2025-11-20 | [8 empty] | 299838 | [6 empty] | 299838 | 17.6977 | 1394386 |  |  | Invoice raised as on 18-12-2025
34 | OMAXE (Chandigarh-Isabela) | 25-26 | 11044135650 | 2025-09-23 | 289083 | 0 |  | 289083 | 289083 | [16 empty] | 0 | 0 | 289083
35 | OMAXE (Chandigarh-Emred-C) | 25-26 | 11044135651 | 2025-09-23 | 289083 | 0 |  | 289083 | 289083 | [16 empty] | 0 | 0 | 289083
36 | Nipl Panipat-CCTV | 25-26 | Final | 2025-10-13 | 9850000 | 0 |  | 9850000 | 9850000 | 2025-12-19 | [8 empty] | 1031222 | [6 empty] | 1031222 | 10.4693 | 8818778
37 | Vishal Infra-November | 25-26 | Final | 2025-10-15 | 2829825 | 0 |  | 2829825 | 2829825 | [16 empty] | 0 | 0 | 2829825
38 | Vishal Infra-Oscar | 25-26 | Final | 2025-10-11 | 2829825 | 0 |  | 2829825 | 2829825 | 2025-12-06 | [15 empty] | 0 | 0 | 2829825 |  |  | RA-01st is done, Invoice to be raise-Pending cleint side.
39 | SPG-ITO-Control Module | 25-26 |  | 2025-11-19 | 249000 | 0 |  | 249000 | 249000 | 2025-11-29 | [8 empty] | 211650 | [6 empty] | 211650 |  | 37350
| AIM Power-Cornerwalk | 25-26 |  | 2025-12-23 | 253705 | 0 |  | 253705 | 253705 | 2025-12-31 | [8 empty] | 253705 | [6 empty] | 253705 |  | 0 |  |  | Po Completed
| I-Thum-Solutrean Building | 25-26 |  | 2025-12-30 | 5820332 | 0 |  | 5820332 | 5820332
0
Grand Total |  |  |  |  | 287785612 | 93132548.8 | 109343401.2 | 88969447 | 198312848.2 |  | 1453395 | 10978461 | 6730463 | 10610813.75 | 9405459.5 | 12804524.5 | 2964927 | 11293980.35 | 5873635 | 1082425 | 329278 | 382493 | 0 | 876877.35 | 85705 | 69358880.75 | 3327.3515 | 123133635.45
Total Billing Booked on Tally till 31-12-2025. | [10 empty] | 72115659.1
Less: Credit Note | [10 empty] | 2756778.35
As per Tally and Working Matched, this is Final Sales Till-30-11-25 | [10 empty] | 69358880.75
(FY.25-26) Month Wise Billing details as per Tally & GST Portal wise
[8 empty] | Sr.No. | Month |  | amount | Remarks
[8 empty] | 1 | Apr'25 |  | 1453395 | Tally Matched as per Cal sheet
[8 empty] | 2 | May'25 |  | 10978461 | Tally Matched as per Cal sheet
[6 empty] | 0 |  | 3 | Jun'25-Delhi |  | 6605463 | Tally Matched as per Cal sheet | June Total-6730463
[8 empty] | 3 | Jun'25UP-Tally-Jun |  | 125000 | Add Embrace in UP Branches rs.125000/-
[8 empty] | 4 | Jul'25 |  | 10610813.75 | Tally Matched as per Cal sheet
Admin Po Value | [7 empty] | 5 | Aug'25 |  | 9405459.5 | Tally Matched as per Cal sheet
[8 empty] | 6 | Sep'25 |  | 12804524.5 | Tally Matched as per Cal sheet
[8 empty] | 7 | Oct'25. |  | 2964927 | Tally Matched as per Cal sheet
[8 empty] | 8 | Nov'25 |  | 11293980.35 | Tally Matched as per Cal sheet
Less | [11 empty] | Tally Matched as per Cal sheet
Finla | [7 empty] | 9 | Dec'25 |  | 5873635 | Tally Matched as per Cal sheet
[8 empty] | Total |  |  | 72115659.1 | Tally matched as Cal. sheet
Non Po | [7 empty] | Less Credit Note till Dec'25 |  |  | 2756778.35 | -
[8 empty] | Final Sales |  |  | 69358880.75 | till Nov_ tally Matched as on 30-11-25
[8 empty] | Final Sales Summary | Up Tally |  | Delhi Tally | Total Sales Till Dec'2025
[9 empty] | 125000 |  | 69233880.75 | 69358880.75
Summary
Installation (MB) billing as on 31-12-25 for party Wise FY-25-26
[8 empty] | Sr.No. | Project |  | Amount | Remarks
[8 empty] | 1 | Grandthum |  | 150731
[8 empty] | 2 | AB Mauri |  | 203432
[8 empty] | 3 | Max Mohali |  | 120986
[8 empty] | 4 | Max Saket |  | 228365
[8 empty] | 5 | Crystaltown |  | 98760
[8 empty] | 6 | SCO-113 |  | 142573 | still handing over Pending as well as RA Bill pending from cleint side
[8 empty] | 7 | Panipat-Old |  | 67050 | Dec'25
[8 empty] | 8 | Nilp-Boom Barrier |  | 177552 | Dec'25
[8 empty] | 9 | Cornerwalk |  | 123170 | Dec'25
[8 empty] | Total Value of MB |  |  | 1312619
[8 empty] | Total Value of Supply |  |  | 68046261.75
[8 empty] | Total Billing as of now-31-12-25 |  |  | 69358880.75

## Billing detail req by Sir-Nov
Summary of Old & New PO Balance, & FY25-26 Billing Details
Billing Details (FY_2025-26) Reporting date:30-11-2025
Total> |  |  |  | 281757875 | 93007548.8 | 109343401.2 | 82678774 | 192022175.2 | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Billing Month | Credit Note | Credit Note | Credit Note | Credit Note | Credit Note | Total Billing (F.Y.25-25) till 30-11-2025 | Bill in FY-24-25 | FY 24-25 & 25-26 | Billing_% 25-26 | Billing_% 24-25 & 2 5-26 | - | - | In Dec'2025 | Report till 29-10-2025.
Sr.No. | Cleint's Name | PO Number | PO Date will be fill | PO Value | Bill till FY-24-25 | OLD PO Balance | PO Value (25-26) | Total PO Value in hand | Apr'2025 | May'2025 | Jun'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Jul'2025 | Aug'2025 | Sep'2025 | Oct'2025 | Nov'2025 | Total Billing_as of now after less Credit Note | Apr'24 to Mar'25 | Total Billing | %tage of PO Value's Billing | %tage of PO Value's Billing | PO_Balance in hand (25-26) | Po Balance (24-25 & 25-26) | RA preared, only Invoice to be raise in Dec'2025 | Billing Type | Project Head Name | Remarks
1 | Angel Hyaat |  |  | 1859780 | 1574780 | 285000 | 0 | 285000 | 0 | [12 empty] | 0 | 1574780 | 1574780 | 0 | 84.6756 | 285000 | 285000 | 285000 |  | Satish Ji
2 | Krihsna Aiims |  |  | 12281602 | 1260654 | 11020948 | 0 | 11020948 | 0 |  |  | 441466.9 | [9 empty] | 441466.9 | 1260654 | 1702120.9 | 4.0057 | 13.8591 | 10579481.1 | 10579481.1 |  |  | Satish Ji
3 | Trump Tower |  |  | 480000 | 363200 | 116800 | 0 | 116800 | 0 | [12 empty] | 0 | 363200 | 363200 | 0 | 75.6667 | 116800 | 116800 |  |  | Mahipal
4 | SCO-113 Lekh |  |  | 1675761 | 1023779.3 | 651981.7 | 473318 | 1125299.7 | 0 |  |  |  |  | 340990 |  | 416432 |  |  |  |  | 282440 | 474982 | 1023779.3 | 1498761.3 | 42.2094 | 89.4377 | 650317.7 | 176999.7 |  |  | Mahipal
5 | M3M R& R |  |  | 11734161 | 1037342.5 | 10696818.5 | 0 | 10696818.5 | 0 |  |  | 1025696 | [9 empty] | 1025696 | 1037342.5 | 2063038.5 | 9.5888 | 17.5815 | 9671122.5 | 9671122.5 |  |  | Mahipal
6 | M3M-Panipat-Old |  |  | 2468800 | 735280 | 1733520 | 0 | 1733520 | 0 | [6 empty] | 785680 | [5 empty] | 785680 | 735280 | 1520960 | 45.3228 | 61.6073 | 947840 | 947840 |  |  | Mahipal |  | 125780151.1
7 | Blue Star-AB Mauri |  |  | 6925030 | 3262387 | 3662643 | 2438531 | 6101174 | - | - | 974211 | 203431.85 |  |  |  | 1668274 | 8283 |  |  |  |  | 2837633.85 | 3262387 | 6100020.85 | 46.5096 | 88.0866 | 3263540.15 | 825009.15 |  |  | Satish
8 | M3M JEWEL - Music System |  |  | 1126004 | 0 | 1126004 | 0 | 1126004 | 0 |  |  |  |  | 114450 | [7 empty] | 114450 | 0 | 114450 | 10.1643 | 10.1643 | 1011554 | 1011554 |  |  | Mahipal
9 | M3M -Paragon - Music System |  |  | 3699991 | 0 | 3699991 | 0 | 3699991 | 0 |  |  |  |  | 267050 | [7 empty] | 267050 | 0 | 267050 | 7.2176 | 7.2176 | 3432941 | 3432941 |  |  | Mahipal
10 | M3M -Jewel Security System | Lekh/Jewel 25/Security System and Access Control Work/LOA/2025/26 |  | 2832390 | 0 | 2832390 | 0 | 2832390 | 0 |  |  |  | 158790 | 110642 |  | 271985 |  |  | 158790 |  |  | 382627 | 0 | 382627 | 13.509 | 13.509 | 2449763 | 2449763 |  | Supply | Mahipal | RA-01st Invoice to be raise
11 | M3M -Paragon-57 Security System | Paryapt/Paragon-57/Security System and Access Control Work/LOA/2025/81 |  | 4100000 | 0 | 4100000 | 0 | 4100000 | 0 |  |  |  | 223703 | 152303 |  | 283010 |  |  | 223703 |  |  | 435313 | 0 | 435313 | 10.6174 | 10.6174 | 3664687 | 3664687 |  | Supply | Mahipal | RA-01st Invoice to be raise
12 | M3M -Corner Walk-Prompt-CCTV | Prompt/Corner Walk/SITC/of CCTV Work for Loft Area/LOA/2024/343 |  | 922583 | 0 | 0 | 922583 | 922583 | 0 | 0 |  |  | 413295 | 208538 | [7 empty] | 621833 | 0 | 621833 | 67.4013 | 67.4013 | 300750 | 300750 |  |  | Mr Pooran
13 | Labotek GGIPU |  |  | 907796 | 0 | 907796 | 0 | 907796 | 0 | 427607 |  | 333718 | [9 empty] | 761325 | 0 | 761325 | 83.8652 | 83.8652 | 146471 | 146471 |  |  | Mr Prakash
14 | Power House Jhajjar |  |  | 780500 | 205595 | 574905 | 0 | 574905 | 130500 | [12 empty] | 130500 | 205595 | 336095 | 22.6994 | 43.0615 | 444405 | 444405 |  |  | Ashu | Completed "The payment is still pending
13 | SPG-ITO Mumbai-ELV |  |  | 6100585 | 3683520 | 2417065 | 0 | 2417065 |  |  | 1443970 | 576963 |  |  |  | 170107 | [5 empty] | 2191040 | 3683520 | 5874560 | 90.6488 | 96.295 | 226025 | 226025 |  |  | Satish Ji & Vijay | Invoice to be raise
14 | SPG-ITO Mumbai-BMS |  |  | 6350710 | 3293305 | 3057405 | 0 | 3057405 | 0 | 510195 | 203362 | 266912 |  | 79040 |  | 50620 | [5 empty] | 1110129 | 3293305 | 4403434 | 36.3095 | 69.3377 | 1947276 | 1947276 |  | Supply | Satish Ji & Pooran | Invoice to be raise
15 | MRC-Jammu |  |  | 3114148 | 1296490 | 1817658 | 0 | 1817658 | 695175 | [12 empty] | 695175 | 1296490 | 1991665 | 38.2456 | 63.9554 | 1122483 | 1122483 |  | Supply | Satish Ji | Invoice raised.
18 | RFL-AMC-Q4 |  |  | 2750000 | 2062500 | 687500 | 0 | 687500 |  | 687500 | [11 empty] | 687500 | 2062500 | 2750000 | 100 | 100 | 0 | 0 |  |  | Sayed & Sandeep | PO Completed
16 | AL SOFTWEB - Grandthum_CCTV Bhutani Group |  |  | 31196662 | 7470651 | 23726011 | 0 | 23726011 | 0 | 1254829 | 2017195 |  | 0 | 1709426 | 742587 |  |  |  | 0 |  |  | 5724037 | 7470651 | 13194688 | 24.1256 | 42.2952 | 18001974 | 18001974 |  |  | Pooran Ji | RA-05th is done Invoice to be raise
17 | RIC-Eco Park |  |  | 73000000 | 44279628 | 28720372 | 0 | 28720372 |  |  |  |  | 411862.5 | 1984800 |  | 395831 | [5 empty] | 2792493.5 | 44279628 | 47072121.5 | 9.723 | 64.4824 | 25927878.5 | 25927878.5 |  |  | Pooran Ji | PI Raises
20 | SPG-Hanumnagarh |  |  | 20680085 | 16246740 | 4433345 | 0 | 4433345 |  |  |  | 4433345 | [9 empty] | 4433345 | 16246740 | 20680085 | 100 | 100 | 0 | 0 |  |  | Pooran Ji | Completed
21 | NCDC-Dyna Filters-ELV |  |  | 3018195 | 2317975 | 700220 | 0 | 700220 | [13 empty] | 0 | 2317975 | 2317975 | 0 | 76.8 | 700220 | 700220 |  |  | Satish Ji
22 | NCDC-Dyna Filters-BMS |  |  | 5232770 | 2902732 | 2330038 | 0 | 2330038 | [13 empty] | 0 | 2902732 | 2902732 | 0 | 55.4722 | 2330038 | 2330038 |  |  | Satish Ji
18 | Max Saket-Delhi- BMS-Hitachi |  |  | 10788650 | 0 | 0 | 10788650 | 10788650 | 0 | 3385398 | 583224 | 11281 | 550862 | 185914 |  | 723777 | 583224 |  |  |  | 185914 | 4671318 | 0 | 4671318 | 43.2984 | 43.2984 | 6117332 | 6117332 |  | Supply | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
19 | Max-Mohali- Acces Control Ahluwalia |  |  | 5232900 | 0 | 0 | 5232900 | 5232900 | - | 1376859 | 300933 |  | 219678 | 1934090 |  | 347980 | [5 empty] | 4179540 | 0 | 4179540 | 79.8704 | 79.8704 | 1053360 | 1053360 |  |  | Mr Pooran | RA5th_ Done Invocie to be raise
20 | Max-Mohali-BMS-Hitachi |  |  | 5247334 | 0 | 0 | 5247334 | 5247334 | - | 2191333 | 490918 |  | 625792 | 567165 |  | 208134 | 490918 |  |  |  |  | 3592424 | 0 | 3592424 | 68.4619 | 68.4619 | 1654910 | 1654910 |  |  | Ajay Chauhan Ravinder Sharama | RA02nd Done Invocie to be raise
21 | Central Park-Old |  |  | 2728200 | 0 | 0 | 2728200 | 2728200 | [5 empty] | 236577 |  | 840924 | [5 empty] | 1077501 | 0 | 1077501 | 39.4949 | 39.4949 | 1650699 | 1650699 |  |  | Mahipal
27 | Nestle AMC for 2 Site Patna & Serampore |  |  | 230765 | 0 | 0 | 230765 | 230765 | 55100 | -55000 | [11 empty] | 100 | 0 | 100 | 0.043334 | 0.043334 | 230665 | 230665 |  |  | Sandeep Kaur | SES Pending Cancelled this PO
22 | Hari Electric Work | 0 |  | 10920 | 0 | 0 | 10920 | 10920 | 10920 | 0 | 0 | [10 empty] | 10920 | 0 | 10920 | 100 | 100 | 0 | 0 |  |  |  | Completed
28 | Nestle Bhiwandi |  |  | 17990 | 0 | 17990 | 0 | 17990 | 17990 | [12 empty] | 17990 | 0 | 17990 | 100 | 100 | 0 | 0 |  |  | Sandeep Kaur | Completed
29 | Nestle Ponda-Goa |  |  | 17990 | -9010 | 27000 | 0 | 27000 | 27000 | 0 | [11 empty] | 27000 | -9010 | 17990 | 100 | 100 | 0 | 0 |  |  | Ashu | Completed
30 | Labotek GGIPU |  |  | 184741 | 0 | 0 | 184741 | 184741 | 156460 | 0 | [11 empty] | 156460 | 0 | 156460 | 84.6915 | 84.6915 | 28281 | 28281 |  |  | Mr Prakash
31 | Leighton Contactors |  |  | 1873300 | 0 | 0 | 1873300 | 1873300 | 360250 | 936650 | 576400 | [10 empty] | 1873300 | 0 | 1873300 | 100 | 100 | 0 | 0 |  |  | HSS | Completed
32 | Angel-Ramai-Haryana | Against V9's Quote |  | 263090 | 0 | 0 | 263090 | 263090 | 0 | 263090 | [11 empty] | 263090 | 0 | 263090 | 100 | 100 | 0 | 0 |  |  | Sanjay | Completed
33 | Embrace Infrasys | EIPL-PO-252606 |  | 125000 | 0 | 0 | 125000 | 125000 |  | 0 | 125000 | [10 empty] | 125000 | 0 | 125000 | 100 | 100 | 0 | 0 |  |  |  | Completed
22 | Grandthum-Access Control | ALSPL/V9/SB/25- 26/WO/-8 |  | 8005040 | 0 | 0 | 8005040 | 8005040 |  |  |  | 3079200 |  | 3869952 | [7 empty] | 6949152 | 0 | 6949152 | 86.8097 | 86.8097 | 1055888 | 1055888
35 | DPS School |  |  | 1050457 | 0 | 0 | 1050457 | 1050457 |  |  |  |  | 1078161 |  |  |  |  | 329278 |  |  |  | 748883 | 0 | 748883 | 71.2912 | 71.2912 | 301574 | 301574 |  |  |  | PI Prepare Bill to be raise on Jul'25 MB Verifcation is pending from Pooran
36 | Marada-Nestle Serampore-Service Call | - |  | 10000 | 0 | 0 | 10000 | 10000 |  |  | 10000 | [10 empty] | 10000 | 0 | 10000 | 100 | 100 | 0 | 0 |  |  |  | Completed
37 | GVD-Switch Billing | - |  | 197750 | 0 | 0 | 197750 | 197750 |  |  | 5250 | 192500 | [9 empty] | 197750 | 0 | 197750 | 100 | 100 | 0 | 0 |  |  |  | Completed
23 | STERLING-Max Gurgaon | 4900000812 |  | 7400000 | 0 |  | 7400000 | 7400000 | [7 empty] | 1816482 | [5 empty] | 1816482 | 0 | 1816482 | 24.5471 | 24.5471 | 5583518 | 5583518
25 | Nestle Raipur- Paid Service | 4561970433 |  | 10000 | 0 |  | 10000 | 10000 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
26 | Nestle Kheda-Paid | 4561931385 |  | 20000 | 0 |  | 20000 | 20000 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 20000 | 20000
24 | Nestle (Ganaur) | 4561964158 |  | 1430300 | 0 |  | 1430300 | 1430300 | [6 empty] | 1430300 | [6 empty] | 1430300 | 0 | 1430300 | 100 | 100 | 0 | 0 |  |  |  | Completed
28 | Avl India Pvt ltd | 40375984 |  | 148000 | 0 |  | 148000 | 148000 |  |  |  |  | 74000 | [8 empty] | 74000 | 0 | 74000 | 50 | 50 | 74000 | 74000
29 | Olive karoke | Music System |  |  | 0 |  | 360000 | 360000 | [13 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 360000 | 0
25 | Nipl Panipat | UTTIRNA/PANIPAT PH-2/SITC Of Automatic BoomBarrier/LOA/2025/68 |  | 10389046 | 0 |  | 10389046 | 10389046 |  |  |  |  | 5649316 | 283605 |  | 1692151 | [5 empty] | 7625072 | 0 | 7625072 | 73.3953 | 73.3953 | 2763974 | 2763974 |  |  |  | Ra done Materil to be deliver
45 | Pixel Info | Return |  | 46300 | 0 |  | 46300 | 46300 |  |  |  | 46300 | [9 empty] | 46300 | 0 | 46300 | 100 | 100 | 0 | 0 |  |  |  | Done
26 | Crystaltown_New | 2000003682, Date:21-08-2025 |  | 639823 | 0 |  | 639823 | 639823 | [6 empty] | 153540 | 894810.35 |  |  |  |  | 408523.35 | 639827 | 0 | 639827 | 100.0006 | 100.0006 | 0 | 0 |  |  |  | Completed
47 | RELAXO RFL-6 (Service) | 2300018047 |  | 31480 | 0 |  | 31480 | 31480 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 31480 | 31480
48 | RELAXO RFL- 9 (Service) | 2300018052 |  | 18550 | 0 |  | 18550 | 18550 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 18550 | 18550
49 | RELAXO RFL- 9 (Service) | 2300018053 |  | 59980 | 0 |  | 59980 | 59980 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 59980 | 59980
27 | RELAXO RFL - 9 (Supply) | 1300005422 |  | 331415 | 0 |  | 331415 | 331415 | [6 empty] | 308865 | [6 empty] | 308865 | 0 | 308865 | 93.1958 | 93.1958 | 22550 | 22550 |  |  |  | Completed
28 | RELAXO -MD House RK Dua |  |  | 16490 | 0 |  | 16490 | 16490 | [6 empty] | 16490 | [6 empty] | 16490 | 0 | 16490 | 100 | 100 | 0 | 0 |  |  |  | Completed
29 | RELAXO RFL - 9 (Supply) | 1300005423 |  | 119040 | 0 |  | 119040 | 119040 | [6 empty] | 118290 | [6 empty] | 118290 | 0 | 118290 | 99.37 | 99.37 | 750 | 750 |  |  |  | Completed
30 | RELAXO RFL-6 (Supply) | 1300005424 |  | 217045 | 0 |  | 217045 | 217045 | [6 empty] | 194855 | 17800 | [5 empty] | 212655 | 0 | 212655 | 97.9774 | 97.9774 | 4390 | 4390 |  |  |  | Completed
31 | OMAXE (Hazratganj-Lacknow) | OML/R5L/11011203477 |  | 737756 | 0 |  | 737756 | 737756 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 737756 | 737756
54 | PSM ENTERPRISES | PSM/BMS/AMRT/25-26/001 |  | 50000 | 0 |  | 50000 | 50000 | [5 empty] | 50000 | [7 empty] | 50000 | 0 | 50000 | 100 | 100 | 0 | 0
32 | RELAXO -AMC | 2300018318 |  | 2839930 | 0 |  | 2839930 | 2839930 | [5 empty] | 709982.5 |  | 709983 | [5 empty] | 1419965.5 | 0 | 1419965.5 | 50 | 50 | 1419964.5 | 1419964.5
33 | OMAXE (Bahadur Garh) | 11011204044 |  | 1694224 | 0 |  | 1694224 | 1694224 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 1694224 | 1694224 | 264563
34 | OMAXE (Chandigarh-Isabela) | 11044135650 |  | 289083 | 0 |  | 289083 | 289083 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 289083 | 289083
35 | OMAXE (Chandigarh-Emred-C) | 11044135651 |  | 289083 | 0 |  | 289083 | 289083 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 289083 | 289083
36 | Nipl Panipat-CCTV | Final |  | 9850000 | 0 |  | 9850000 | 9850000 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 9850000 | 9850000
37 | Vishal Infra-November | Final |  | 2829825 | 0 |  | 2829825 | 2829825 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 2829825 | 2829825
38 | Vishal Infra-Oscar | Final |  | 2829825 | 0 |  | 2829825 | 2829825 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 2829825 | 2829825
39 | SPG-ITO-Control Module |  |  | 249000 | 0 |  | 249000 | 249000 | [13 empty] | 0 | 0 | 0 |  | 0 | 249000 | 249000 | 211650
Grand Total |  |  |  | 281757875 | 93007548.8 | 109343401.2 | 82678774 | 192022175.2 | 1453395 | 10978461 | 6730463 | 10610813.75 | 9405459.5 | 12804524.5 | 2964927 | 11293980.35 | 1082425 | 329278 | 382493 | 0 | 876877.35 | 63570950.75 | 93007548.8 | 156578499.55 | - |  | 128451228.45 | 125179379.45 | 761213
Total Billing Booked on Tally till 30-11-2025. | [8 empty] | 66242024.1
Less: Credit Note | [8 empty] | 2671073.35
As per Tally and Working Matched, this is Final Sales Till-30-11-25 | [8 empty] | 63570950.75
Final Month Wise Billing details as per Tally Acts.
[7 empty] | Sr.No. | Month | amount | Remarks
[7 empty] | 1 | Apr'25 Tally billing amt | 1453395 | Tally Matched as per Cal sheet
[7 empty] | 2 | May'25 Tally billing amt | 10978461 | Tally Matched as per Cal sheet
[5 empty] | 0 |  | 3 | Jun'25-Delhi Tally billing amt Till 26-06-25 | 6605463 | Tally Matched as per Cal sheet | June Total-6730463
[7 empty] | 3 | UP-Tally-Jun | 125000 | Add Embrace in UP Branches rs.125000/-
[6 empty] | Nilp | 4 | Jul'25 Tally billing amt | 10610813.75 | Tally Matched as per Cal sheet
Admin Po Value | [6 empty] | 5 | Aug'25-till 20-08-25 Tally billing amt | 9405459.5 | Tally Matched as per Cal sheet
[7 empty] | 6 | Sep'25-till 30-09-25 Tally billing amt | 12804524.5 | Tally Matched as per Cal sheet
[7 empty] | 7 | Oct'25-till 31.-10-25 Tally billing amt | 2964927 | Tally Matched as per Cal sheet
[7 empty] | 8 | Oct'25-till 30-11-25 Tally billing amt | 11293980.35 | Tally Matched as per Cal sheet
Less
Finla | [6 empty] | Total |  | 66242024.1 | Tally matched as Cal. sheet
[7 empty] | Less Credit Note on Nov'25 |  | 2671073.35 |  | Up Tally | Delhi Tally | Remarks
[7 empty] | Final Sales |  | 63570950.75 | till Nov_ tally Matched as on 30-11-25 | 125000 | 63445950.75 | Matched-30-11-25
Non Po | [23 empty] | Summary
Installation (MB) billing as on 30-11-25 for party Wise FY-25-26
[24 empty] | Sr.No. | Project | Amount | Remarks
[24 empty] | 1 | Grandthum | 150731
[24 empty] | 2 | AB Mauri | 203432
[24 empty] | 3 | Max Mohali | 120986
[24 empty] | 4 | Max Saket | 228365
[24 empty] | 5 | Crystaltown | 98760
[24 empty] | 6 | SCO-113 | 142573 | still handing over Pending as well as RA Bill pending from cleint side
[24 empty] | 7 | Panipat-Old | 67050 | Dec'25
[24 empty] | 8 | Nilp-Boom Barrier | 177552 | Dec'25
[24 empty] | 9 | Cornerwalk | 123170 | Dec'25
[24 empty] | Total Value of MB |  | 1312619
[24 empty] | Total Value of Supply |  | 62258331.75
[24 empty] | Total Billing as of now-30-11-25 |  | 63570950.75

## Project details
S. No | Project | Client | Items | Status | PO Date | Completion Date | Project Period | Technical Manager | Contractor | Site Visit | All TDS | Drawings | Material Delivery
1 | NTPC- Ecopark | RIC | CCTV | In Progres | 2022-05-27 |  | 3 years, 6 months, 7 days | Puran | Self
2 | NCDC- HSCC | Dyna Filter | CCTV, FAS, BMS | In Progres | 2024-01-20 |  | 1 years, 10 months, 11 days | Satish | Shivam Dubey
3 | TATA Power tamil Nadu | Voltas | BMS | In Progres |  | 2025-10-30 | 0 | Anil | Anil Kosare |  |  | As Built Drawings
4 | Trump Tower M3M Grugaon | M3M | BGM | In Progres | 2024-03-28 |  | 1 years, 8 months, 3 days | Mahipal | Self |  |  |  | Done
5 | AIIMS - Delhi | Krishna Const. | CCTV, FAS, PA, EPBAX | In Progres | 2024-05-23 |  | 1 years, 6 months, 8 days | Satish | Rohit/ Maninder |  |  |  | In Progress
6 | M3M - Panipat | M3M | Boom Barriers | In Progres | 2024-07-19 | 2025-11-15 | 1 years, 4 months, 12 days | Mahipal | Self |  |  |  | In Progress
7 | M3M- Capitol -113 R&R | M3M | CCTV , Boom , Access | In Progres | 2024-07-16 |  | 1 years, 4 months, 15 days | Mahipal | Tarun |  |  |  | In Progress
8 | M3M- SCO113 | M3M | CCTV , Boom Barriers | In Progres | 2024-07-11 | 2025-08-09 | 1 years, 4 months, 20 days | Mahipal | Shivan Dubey |  |  |  | In Progress
9 | AB Mauri | Bluestar | FAS | In Progres | 2024-07-16 |  | 1 years, 4 months, 15 days | Satish | Sunny |  |  | AB Mauri | Pending
10 | ITO Mumbai | SPG | FAS PA | In Progres | 2024-07-03 | Completed | 0 | Vijay Satish - Technical | Khalid Sunny |  |  |  | Pending
11 |  | SPG | BMS | In Progres | 2024-11-18 | 2025-11-05 | 1 years, 0 months, 13 days | Vijay Satish - Technical
12 | Jammu Railway Station | MRC | BMS | In Progres | 2024-12-09 |  | 0 years, 11 months, 22 days | Satish | Self |  |  |  | Pending
13 | Grandthum Ref.No.289 (A) | Bhutani Group | CCTV | In Progres | 2024-12-04 | 0 | 0 years, 11 months, 27 days | Ram, Pooran | Arun |  |  |  | Pending
14 | Grandthum Ref.No.309 | Bhutani Group | Swing Barrier | In Progres | 2025-05-12 |  | 0 years, 6 months, 19 days | Ram, Pooran | Arun |  |  |  | Pending
15 | GGSIPU | Labotek | FAS, PA, | In Progres | 16-04-2025 |  | 0 years, 7 months, 15 days | Sanjay | Shivam Dubey
16 | Max saket | Hietachi | BMS | In Progres | 2025-03-18 |  | 0 years, 8 months, 13 days | Ajay Chuahan, Vijay, Ravinder Sir | New Labh Sharma |  | Approved | Partial
17 | M3M- Jewel (Ref.297) | M3M | CCTV , Boom , ACS |  | 2025-01-22 |  | 0 years, 10 months, 9 days | Mahipal | V9 |  |  |  | Partial delivery
18 | M3M- Jewel | M3M | Music |  | 2025-01-20 |  | 0 years, 10 months, 11 days
19 | M3M- Paragon (296) | M3M | CCTV, Boom Barrier, ACS |  | 2025-02-24 |  | 0 years, 9 months, 17 days
20 | M3M- Paragon (295) | M3M | Music Systen |  | 2025-01-20 |  | 0 years, 10 months, 11 days | Mahipal
21 | Max Mohali | Hitachi | BMS |  | 2025-03-04 | 2025-11-15 | 0 years, 8 months, 27 days | Ravinder Sir | Sunny |  | BMS TDS | BMS Drawings
22 | Max Mohali | Ahluwalia | ACS |  | 2025-04-11 | 2025-11-05 | 0 years, 7 months, 20 days | Mahipal | V9
23 | Central Park | Kabir | CCTV | In Progres | 2025-03-20 |  | 0 years, 8 months, 11 days | Vijay |  |  | Appoved
24 | Central Park Flower Valley | Crystaltown | CCTV | In Progres | 21-8-25 |  | 0 years, 3 months, 10 days | Vijay |  |  |  | not received
25 | Max Gurgaon (Ref.315) | Sterling Wilson | BMS | To Be Start | 14-07-2025 |  | 0 years, 4 months, 17 days | Ravinder Sir |  |  |  | not received
26 | NILP Panipat | M3M | Boom Barriers | In Progres | 2025-01-07 |  | 0 years, 10 months, 24 days | Mahipal |  |  | Appoved | not received | Partial delivery
27 | NILP Panipat | M3M | CCTV | To Be Start | 2025-10-13 | 2025-10-13 | 0 years, 1 months, 18 days |  | pending |  | Pending | not received | pending
28 | Karaoke | M3M | Music | To Be Start | 2025-08-08 |  | 0 years, 3 months, 23 days | Mahipal |  |  |  | not received | pending
29 | Corner Walk | M3M | CCTV | In Progres | 2025-03-25 |  | 0 years, 8 months, 6 days | Vijay |  |  |  | not received | Partial delivery
30 | RFL - 9 (326) | Relaxo | CCTV |  |  |  | 0
31 | RFL - 9 (327) | Relaxo | CCTV |  |  |  | 0
32 | RFL - 6 (328) | Relaxo | CCTV |  |  |  | 0
33 | OMAXE- Hazratganj(329) | Omaxe | CCTV | To Be Start | 2025-03-09 |  | 0 years, 8 months, 22 days
35 | OMAXE Bahadur Garh (332) | Omaxe | CCTV | To Be Start | 2025-09-22 |  | 0 years, 2 months, 9 days
36 | OMAXE Chandigarh-Isabela (333) | Omaxe | CCTV | To Be Start | 2025-09-22 |  | 0 years, 2 months, 9 days |  |  | Today By Satish
37 | OMAXE Chandigarh-Emred-C (334) | Omaxe | CCTV | To Be Start | 2025-09-22 |  | 0 years, 2 months, 9 days |  |  | Today By Satish
38 | DRDO - Srinigar ( Oscar) | Vishal Infra | CCTV | To Be Start | 2025-10-17 |  | 0 years, 1 months, 14 days |  |  | Done by Aftab
39 | DRDO - Srinigar ( Oscar) | Vishal Infra | CCTV | To Be Start | 2025-10-17 |  | 0 years, 1 months, 14 days
0
0
0
0
0
0
0
753798
966376
122369
1175649
3018192

## PO value by Admin
PO VALUE MONTH WISE- 2025-26
Ref.no | S.no | PO DATE | PO NUMBER | PARTY NAME | PO VALUE | 01st Delivery date | 01st RA Date | 01st Billing Date | Period of Gap as per PO Date as per Delivered Material | Period of Gap as per PO Date as per Final RA-Bill | Period of Gap as per PO Date as per Final-Tax Invoice | Remarks
301 | 1 | 2025-04-01 | HMN/PO/24-25/109 | Hitachi MGRM Net ( Max Saket) | 10788650 | 2025-04-01 | 2025-04-21 | 2025-07-25 | 0 | -20 | -115
302 | 2 | 2025-04-01 | 4561695925 | AMC of CCTV Nestle Serampore | 110000 | - | - | 2025-12-11 | - | 0 | -254
303 | 3 | 2025-04-01 | 4561703703 | AMC of CCTV Nestle Patna | 120765
304 | 4 | 2025-04-01 | KSSMSPL/WO/CP-III/24-25/12 | Kabir Super Speciality Medical Service Pvt.Ltd.( Central Park) | 2728200
305 | 5 | 2025-04-01 | Prompt/Corner Walk/SITS of CCTV Work for Loft Area/LOA/2024/343 | Prompt Engineering Pvt.Ltd.( Corner Walk) | 922583
306 | 6 | 2025-04-01 | LBT/0046/2024-25/W/T2 | Labotek- GGSIPU-Dwarka | 23850
307-A | 7 | 2025-03-04 | HMN/PO/25-26/2 | Hitachi MGRM Net ( Max Mohali) | 5247334.46
307-B | 8 | 2025-11-04 | ACIL/WO/ELECT/MAX-Mohali/2025-26/0259 | Ahluwalia Contracts India Limited ( Max Mohali) | 3700000
308 | 9 | 16-04-2025 | LBT/0006/2025-26/W/T2 | Labotek- GGSIPU-Dwarka | 132710
309 | 10 | 2025-12-05 | ALSPLv9 TECH/SWING BARRIER/2025-26/WO-8 | Alsoftweb- Grandthum (Swing Barrier) | 8005040
310 | 11 | 15-05-2025 | EIPL-PO-252606 | EMBRACE INFRASYS PVT LTD | 125000
311 | 12 | 21-05-2025 | 8023960 | Leighton India Contractors Pvt.Ltd. | 1873300
312-A | 13 | 26-05-2025 | DPS/ MR/EO/2025-26/CCTV/ 1318/1 | DPS Mathura Road | 555590
312-B | 14 | 26-05-2025 | DPS/MR/EO/2025-26/CCTV/ 1318/2 | DPS Mathura Road | 494867
313 | 15 | 30-06-2025 | LEKH/SCO 113/CCTV BOOM BARRIER/LOA/2024/91/AMEND-01 | M3M Market SCO-113 | 473318
314 | 16 | 2025-01-07 | UTTIRNA/PANIPAT PH-2/SITC Of Automatic BoomBarrier/LOA/2025/68 | Boom Barrier NIPL Panipat | 10389046
315 | 17 | 14-07-2025 | 4900000812 | STERLING AND WILSON PVT LTD | 7400000
316 | 18 | 16-07-2025 | 4561970433 | Nestle India Ltd (DC Raipur) | 10000
317 | 19 | 16-07-2025 | 4561931385 | Nestle India Limited-Nagpur& Kheda | 20000
339 | 20 | 16-07-2025 | 4700000586 | Bluestar - AB Mauri (Amended PO against Ref.no-269) | 2550131
318 | 21 | 17-07-2025 | 4561964158 | Nestle India Ltd (Ganaur) | 1430300
319 | 22 | 18-07-2025 | 40375984 | AVL India Private Ltd | 148000
330 | 23 | 2025-11-08 | PSM/BMS/AMRT/25-26/001 | PSM ENTERPRISES | 50000
320 | 24 | 18-08-2025 | OLIVE/Trump Tower/Supply of Music System/PO/2025/165 | Olive Realcon Pvt Ltd | 360000
321 | 25 | 19-08-2025 | ACIL/WO/ELECT/MAX-Mohali/2025-26/0259 | Ahluwalia Contracts India Limited (Amended Max Mohali) | 1532900
322 | 26 | 21-08-2025 | 2000003682 | Crystaltown Hospitality Services Pvt Ltd | 640694 | [6 empty] | 4818.65
323 | 27 | 2025-01-09 | 2300018047 | RELAXO RFL-6 | 31480
324 | 28 | 2025-01-09 | 2300018052 | RELAXO RFL- 9 | 18550
325 | 29 | 2025-01-09 | 2300018053 | RELAXO RFL- 9 | 59980
326 | 30 | 2025-02-09 | 1300005422 | RELAXO FOOTWEARS LIMITED RFL - 9 | 331415
327 | 31 | 2025-02-09 | 1300005423 | RELAXO FOOTWEARS LIMITED RFL - 9 | 119040
328 | 32 | 2025-02-09 | 1300005424 | RELAXO RFL-6 | 217045
329 | 33 | 2025-03-09 | OML/R5L/11011203477 | OMAXE TURNING DREAMS INTO REALITY (Hazratganj-Lacknow) | 737756
331 | 34 | 19-09-2025 | 2300018318 | RELAXO FOOTWEAR LIMITED | 2839930
332 | 35 | 23-09-2025 | 11011204044 | OMAXE TURNING DREAMS INTO REALITY (Bahadur Garh)\ | 1694224
333 | 36 | 23-09-2025 | 11044135650 | OMAXE TURNING DREAMS INTO REALITY (Chandigarh-Isabela) | 289083
334 | 37 | 23-09-2025 | 11044135651 | OMAXE TURNING DREAMS INTO REALITY (Chandigarh-Emred-C) | 289083
336 | 38 | 2025-11-10 | VIL/1222/PO/2025/0026 | Vishal Infrastructure Ltd-(Oscar) | 2829825
337 | 39 | 13-10-2025 | UTTIRNA/NILP,Panipat /PH-2/SITC of CCTV Work/LOA/2025/75 | NILP CCTV Panipat | 9850000
338 | 40 | 15-10-2025 | VIL/2122/PO/2025/0029 | Vishal Infrastructure Ltd-(November) | 2829825
340 | 41 | 19-11-2025 | SPG/MUMBAI/19.11.2025/001 | ITO Mumbai | 249000
341 | 42 | 23-12-2025 | 32 | AIM POWER SOLUTION- M3M Trump Tower | 253705
305-B | 43 | 20-12-2025 | Prompt/Corner Walk/SITS of CCTV Work for Loft Area/LOA/2024/343 Amended 1 | Prompt Engineering Pvt.Ltd.( Corner Walk) | 216636
342 | 44 | 30-12-2025 | SBTL/WO/ITHUM73/2025-26/002 | I Thum World -( M/s Solutrean Building Technologies Pvt ltd) | 5820332
Total |  |  |  |  | 88509187.46
Month Wise Summary
|  |  | Months | Value
|  |  | Aprail | 23774092
|  |  | May | 11053797
|  |  | June | 473318
|  |  | July | 21947477
|  |  | August | 2583594
|  |  | September | 6627586
|  |  | October | 15509650
|  |  | November | 249000
|  |  | December | 6290673
|  |  | Total | 88509187